## Slide 1: Events and Multimedia Services EMS-led Events Working Group RECAP AND LESSONS-LEARNED Événements et services multimédia Groupe de travail des événements organisés par ESM SOMMAIRE ET LEÇONS APPRISES

## Slide 2: Objective of the EMS-led Events Working Group
In April, with the announcement of the suspension of all in-person events and moving them to a virtual format, the EMS-led Events Working Group was established.
At the start of the pandemic, our in-house production studio was not accessible due to the isolation rules.
So the group was given the objective of finding the best virtual delivery platforms that would meet the School’s short-term and long-term needs. A key consideration was also to ensure business continuity during the COVID-19 response and whatever comes next.
The group was also tasked with identifying the best short-term solution for our current deliveries from April until now.
Objectif du groupe de travail des événements organisés par ESM
En avril, avec l'annonce de la suspension de tous les événements en personne et de leur transfert à un format virtuel, le groupe de travail des événements organisés par le ESM a été créé.
Au début de la pandémie, notre studio de production interne n'était pas accessible en raison des consignes d'isolement.
Le groupe s'est donc vu confier l'objectif de trouver les meilleures plateformes de diffusion virtuelle qui répondraient aux besoins à court et à long terme de l‘École. Une considération clé était également d'assurer la continuité des activités pendant la réponse à la COVID-19 et ce qui arrivera par la suite.
Le groupe a également été chargé d'identifier la meilleure solution à court terme pour nos livraisons actuelles, d'avril à aujourd'hui.
Notes: Once approved, the event manager assigned to your event will contact you in order to discuss the requirements for your event and will include the marketing advisor assigned to your business line.
EMS will also be responsible for managing registrations and will share the webcast link with participants 24 hours prior to the event.

## Slide 3: Recap - April to August 2020
In April 2020, the Working Group began to assess the situation.
It was determined that the WG’s first focus was to minimize any negative impacts on our participants. In response, the best short-term decision was to stay with the corporately endorsed MSTeams platform + the existing webcast provider (which is Collaborate Video).
An evaluation grid then was drafted and there was back and forth discussions during the initial meetings in April and May where the WG explored which platforms to evaluate, which criteria were important to research, how to evaluate them and how to test them.
In addition to this though, EMS captured logistical lessons learned and key points to use going forward. We also created helpful guidelines for speakers and moderators to help them to adapt to their virtual participation.
En avril 2020, le groupe de travail a commencé à évaluer la situation.
Il a été déterminé que le premier objectif du groupe de travail était de minimiser les impacts négatifs sur nos participants. En réponse, la meilleure décision à court terme a été de rester avec la plateforme MSTeams approuvée par l‘organisation + le fournisseur de webdiffusion existant (qui est Collaborate Video).
Une grille d'évaluation a ensuite été rédigée et des discussions ont eu lieu lors des premières réunions de avril et mai, au cours desquelles le groupe de travail a examiné les plateformes à évaluer, les critères importants à rechercher, la manière de les évaluer et de les tester.
En plus, ESM a noté des leçons apprises et des points clés au niveau logistique à utiliser à l'avenir. Nous avons également créé des directives utiles pour les conférenciers et les modérateurs afin de les aider à s’adapter à leur participation virtuelle.
Sommaire - avril à août 2020

## Slide 4: Six Key Points to Remember on the Logistics Side / Six points clés à retenir au niveau logistique
Work with EMS Early (6-8 Weeks Before your Event)
Dry Runs are Important
Brief your Speakers Well (Share tips and tricks through conference calls and dry runs)
Empower your Moderator to Deal with Issues Live
Have Backup Plans
Host a Post Mortem Meeting: Apply Lessons-Learned on Future Events
Travailler avec ESM tôt (6-8 semaines avant votre événement)
Les simulations « Dry Runs » sont importantes
Bien informer vos conférenciers (partager les trucs et astuces par le biais de conférences téléphoniques et de simulations « dry runs »)
Donner à votre modérateur les moyens de traiter les enjeux en direct
Avoir des plans de contingente
Organiser une réunion post-mortem : Appliquer les leçons apprises aux événements à venir

## Slide 5: Supporting Documents to Share
Tips and tricks for speakers participating virtually
Tips and tricks and protocols for speakers participating onsite
Documents d’appui à partager
Trucs et astuces pour les conférenciers participant virtuellement
Trucs et astuces et protocoles pour les conférenciers participant sur place

## Slide 6: Thank You! Merci!
Jennifer Calegoure, Director/Directrice, EMS/ESM jennifer.calegoure2@canada.ca
Chantal Beaudin, Manager/Gestionnaire, EMS/ESM chantal.beaudin@canada.ca