## Slide 1: Adopting the Canada.ca Design Update and proposed next steps
Digital Transformation Office #canadadotca
September 2020

## Slide 2: Why Adopt the Canada.ca design
Aiming to create a joined up, consistent public web presence
Joined up experience facilitates user task success
Consistency across the GC web presence necessary for trust
Consistency/trust even more important in current online environment rife with misinformation and scams

## Slide 3: What adopting the design means
Mandatory elements of the Canada.ca design:
  Header and footer
  Typography
  Colour scheme
  Default layout
  Mandatory page templates
See details in the design system: https://www.canada.ca/en/treasury-board-secretariat/services/government-communications/canada-content-information-architecture-specification/mandatory-elements.html

## Slide 4: Ways to implement
Update your site:
Use the Canada.ca theme in WET (aka GCweb)
Leverage Centrally Deployed Templates Solution (CDTS)
Migrate to MWS:
Contact Principal Publisher
Details on GCpedia: https://www.gcpedia.gc.ca/wiki/Adopting_the_Canada.ca_design

## Slide 5: Original deadlines for adopting the design
March 2020: main institutional websites
March 2021: remainder of web presence
This fiscal was to be the year for updating web apps etc.
But COVID response has limited progress:
  Resources shifted to COVID response work
  COVID has impacted some depts more than others

## Slide 6: Progress to date - main sites
Jan 2019: launch of Canada.ca design on AEM - approx. 24 institutional main sites
Dec 2019: 32 main sites
Mar 2020: 37 main sites
Sep 2020: 40 main sites*
* includes 2 departments underway but not yet finished

## Slide 7: Kudos
Several departments have continued this work during the pandemic:
CanNor - partial adoption, work ongoing
Infrastructure Canada - partial adoption, work ongoing
NRCan - launched in June
PSPC - partial adoption, work ongoing
WAGE - work ongoing, launch to come this fall

## Slide 8: Recommended approach
Strategy:
Leave implementation deadlines as is
Ask depts to report status, publish results
Create extension process
Offer assistance - workshops, guides, etc.
Rationale:
Given increasing importance of maintaining trust, keep depts. moving on this work
Ability to request extensions gives flexibility to depts impacted by COVID

## Slide 9: Proposed next steps
Update GCpedia presence - new status reporting materials, extension process info
Email from TBS to Heads of Comms to request status and explain how to request extensions
Parallel communications via DTO mailing lists etc.
Publish status reporting - release status info at the GC level

## Slide 10: Discussion
Is this a realistic approach?
How can it be improved?
What can TBS do to help?
Send feedback to: dto.btn@tbs-sct.gc.ca