## About this document
IMPORTANT INFORMATION ABOUT THIS DOCUMENT–MUST READ BEFORE BEGINNING
The calendar portion located on the right of the “CM-PM integrated plan” worksheet is auto-filled based on the information entered in the “Status”, “Start date” and “End date” columns, and on the formula of the “Days” column.
The worksheet provides a visual representation of the schedule; however, there is no link between activities or delays as there would be in Microsoft Project.
1. This worksheet has elements that should not be deleted; otherwise, the functionality will be compromised. The following elements should not be removed or modified:
- Rows 1-8, except for the text in red and the titles for row 7 columns.
- Note: row 8 is hidden and contains the formula that highlights the current day in the schedule; do not remove!
- Columns “Status”, “Start date”, “End date” and “Days”
- ALL columns to the right of the “Days” column, except for the legend at the very top, if you need to modify it.
- The scroll bar at the top of the schedule
2. Project start date: Before using the schedule, you must specify the start date in cell I3. If you wish to hide this information for printing purposes, you can change the colour of the cells (F3 to I3) and font to white.
3. Scrolling increment: Changing the number in cell I4 will make you move forward in the schedule. 1 increment = 1 day. You can also use the scroll bar in the schedule to do the same. If you wish to hide this information for printing purposes, you can change the colour of the cells (F4 to I4) and font to white.
4. Scroll bar: If you click anywhere on the scroll bar (at the top of the schedule) and don’t move your mouse, it will continue to scroll by increments of 2 indefinitely until you move your mouse, this in both directions. To quickly return to the project start, you can type 0 in cell I4.
5. Adding/removing rows:
- Row 9 is an example and should be removed. You can also delete any of the activity rows that do not apply to your project.
- Always ensure to add rows below row 9 (first row) or above row 130 (last row) to ensure they are captured in the formulas.
- Once you’ve inserted new rows, you will need to copy the formatting into those new rows by copy/pasting an entire existing row. You can use any activity row for this or one of the blank ones located at the bottom.
6. Adding/removing columns:
- Adding additional columns can be done as long as it is to the left of the “Days” column.
- You can remove any column with the exception of the “Status”, “Start date”, “End date” and “Days” columns.
7. Columns:
- Type of activity: Use the pull down list to select.
- Activity: The activities listed here are typical of workplace modernization projects, but may not apply to your specific project.
- Lead: Write the name of the person or group leading the activity.
- ADKAR element: Use the pull down list to select. Only applicable to CM activities, for other activities use N/A.
- Steps/Notes: Enter any additional information required for the activity.
- Status: Use the pull down list to select. The status selected changes the colour of the cells in the calendar portion on the right (once the "Start date" and "End date" columns are filled). The status does not impact the "Progress" column.
- Progress: Enter any value between 0 and 100. Incremental grey shading will be automatically applied in that cell. The information in this column is not linked to any other column. For example, marking an activity as “Complete” in the “Status” column will not mark the “Progress” cell as 100%; it needs to be done manually.
- Start date: Enter start date in the format shown. Date must be after the “Project start date”.
- End date: Enter end date in the format shown. Date must be at least 1 day after the “Start date”, and must be after the “Project start date”.
- Actual end date: Enter actual end date in the format shown. The information in this column has no impact on the calendar portion of the worksheet.
- Days: Automatically generated from the information in “Start date” and ‘”End date” columns. Do not enter manual numbers.
8. Text in red in the worksheet needs to be modified:
- Row 1: Client name, Project name, Address
- Row 2: Created by
- Row 3: Project start date (see item 2 above)
- Row 6: Date
9. Text in blue indicates activities that are recurring and may need to be copied multiple times in the schedule.
HOW TO USE THIS WORKSHEET
By default, the rows are sorted by "activity type" and are not necessarily in chronological order. The proposed CM activities have been populated based on best practices and most common CM activities that we have seen in workplace modernization projects. They may not all apply to your project.
It is possible for a CM activity to correspond to more than one ADKAR element; you can select the most prominent one and add a note in the "Steps/Notes" column, as required.
- Once you’ve set up the worksheet as described above, you should start by validating the information that has been pre-populated in the “Type of activity”, “Activity” and “ADKAR element” columns.
- Use the major project milestones or project schedule provided by the project management team and build your CM activities based on those.
- Then, fill in the dates and status.
- Once your dates are filled in, you can sort them by clicking the arrow in the column title and all your activities will be in sequential order.
- You can filter the information in any column (A to K) by clicking the arrow in the column title cell.

## CM-PM integrated plan
Client name‒Project name Address
Created by: xxxx | [9 empty] | Legend: | Not started |  |  |  |  | On track |  |  |  |  | Delayed |  |  |  |  | Late |  |  |  |  | Complete
[5 empty] | Project start date: |  |  | 2020-11-12
[5 empty] | Scrolling increment: |  |  | 0 |  |  | November | [20 empty] | December
Change management approach and schedule Date : xx-xx-xx | time axis 2020-11-12 to 2021-01-06
Type of activity | Activity | Lead | ADKAR element | Steps/Notes | Status | Progress | Start date | End date | Actual end date | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
CM-Engagement | EXAMPLE ACTIVITY | John Doe | N/A |  | Complete | 80% | 2020-11-12 | 2020-12-02 |  | 20
PM-Facilities¦Assets¦Interior design | Project start |  | N/A |  | Complete | 0% | 2020-11-12 | 2020-12-12 |  | 30
PM-Facilities¦Assets¦Interior design | New location decision |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Functional programming |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Preliminary space planning |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Design concept |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Inclusivity applied in office design |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Ergonomics considered in all workpoints |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | More choices of workpoint types |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Shared workplace (unassigned seating) |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Lockers |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Collaboration areas |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Social (or non work-related activities) areas |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Variety of work zones |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Move to swing space |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Project implememtation (incl. Construction) |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Extended hours for access to departmental building |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Access to healthy environment (e.g. gyms, healthy foods, bike racks, etc.) |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Smart office spaces (auto blinds, auto lights, temperature regulation, etc.) |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Move to new space |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Facilities¦Assets¦Interior design | Green transportation between buildings |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Computing device: going from fix to portable |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Updated computing device: new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Phone devices: going from fix to portable |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Updated phone devices: new functionnalities |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Secret/classified network: new common IT tools and processes |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | VPN: increased connectivity and mobility |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Print-on-demand: new tool |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Videoconferencing: new IT tools |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Instant messaging: new IT tools |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Collaboration tools: new IT tools |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Collaboration platforms: new IT tools |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Accessibility of applications via phones: new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Digital signatures: new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | GC email: new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Reservation system: new IT tools |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Wi-Fi: new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information technology | Public Wi-Fi: increased connectivity |  | N/A |  | Not started | 0% |  |  |  | 1
PM-HR¦OHS¦People management | Objective/deliverable-based performance measurement |  | N/A |  | Not started | 0% |  |  |  | 1
PM-HR¦OHS¦People management | Updated policies to integrate greening and sustainability |  | N/A |  | Not started | 0% |  |  |  | 1
PM-HR¦OHS¦People management | Use VR training |  | N/A |  | Not started | 0% |  |  |  | 1
PM-HR¦OHS¦People management | Leading and standing-up program to support culture changes (modern, agile and flexible work) |  | N/A |  | Not started | 0% |  |  |  | 1
PM-HR¦OHS¦People management | Consistent application of GC-wide OHS policies |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | GC-wide IM policies implementation |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Develop employees' ability to share and collaborate on documents using a cloud-based system |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Manage digital documents throughout the lifecycle |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Digitalization strategy: reduce paper storage space |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Centralized document management system |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Cloud file-sharing solution |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Ability to work on secret materials from more than one workpoint |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Reduce electronic duplication: new tool or functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Multiple security classification levels: new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Auto classification of documents (GCdocs): new functionnality |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Imaging services: new tool |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Information management | Moving to paper-light or paperless |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Robust security awareness program for employees |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Application of security classication on information (Document marking) |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Rigouress security classification process |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Consistent emergency notifications to all employees at the same time |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Single identity management system |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Broaden employees access to locations |  | N/A |  | Not started | 0% |  |  |  | 1
PM-Security | Access to secret network for those who need it |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Dedicate a CM resource |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Define what is changing |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Determine your organization's level or readiness to change |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Identify key stakeholders, as well as the types of input they require and what kind of communication they might need |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Identify and assess the sponsor and champions |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Define the approach needed to manage change given the unique characteristics of your project |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Identify steps that the sponsor will need to take to ensure effective sponsorship from other leaders |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Define which metrics are the most meaningful, as well as establish a cadence for collecting and reviewing data |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Define a communication plan |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Define an engagement plan |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Define a training plan |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Monitor modernization program performance |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Monitor CM program performance |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Monitor employee adoption (pulse check survey) |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Make necessary adjustments to CM plan |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Create a CM sustainability plan |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Evaluate the activities implemented and the program, and create a final report |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Program | Create and share lessons learned |  | N/A |  | Not started | 0% |  |  |  | 1
CM-Communication | Kick-off town hall with employees (announce project and vision) |  | Awareness |  | Not started | 0% |  |  |  | 1
CM-Communication | Fact sheets |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Communication | FAQs |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Communication | Ongoing project communication via intranet/newsletter |  | Awareness |  | Not started | 0% |  |  |  | 1
CM-Communication | Announce approved floor plans |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Communication | Announce selected colour scheme |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Communication | Announce typical furniture layouts |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Communication | Project sponsor quarterly email update on project |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Communication | Senior leader(s) quarterly communication on new way of working |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Communication | Send initial move information |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Communication | Send frequent move information |  | Awareness |  | Not started | 0% |  |  |  | 1
CM-Communication | Send digital welcome kit |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Engagement | Manager project discussions at team meetings (Q&As, etc.) |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Pre-occupancy survey |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | GCworkplace 101 workshop with employees |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Engagement | Virtual tour of ABW spaces |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Functional programming engagement with employees |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Create employee committee (change agents) |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Manager discussions on new ways of working at team meetings |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Engagement | Quarterly employee pulse check on change adoption |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Pop-up GCworkplace |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Launch of live-in program/pilot space |  | Ability |  | Not started | 0% |  |  |  | 1
CM-Engagement | Expert panels |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Engagement | Employee-to-employee panels |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Engagement | Create employee committee (on etiquette) |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Engagement | Employee involvement activities (selection of artwork, room naming, etc.) |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Engagement | Recognize and reward employees adopting the new ways of working |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Engagement | Paper clean-up activity |  | Ability |  | Not started | 0% |  |  |  | 1
CM-Engagement | Celebration |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Engagement | Post-occupancy survey |  | Desire |  | Not started | 0% |  |  |  | 1
CM-Training | Leadership Toolkit |  | Ability |  | Not started | 0% |  |  |  | 1
CM-Training | Manager Toolkit |  | Ability |  | Not started | 0% |  |  |  | 1
CM-Training | Change agent Toolkit |  | Ability |  | Not started | 0% |  |  |  | 1
CM-Training | GCdocs refresher course |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Training | Clean desk refresher course |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Training | Mobile device training |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Training | New application training |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Training | Office ergonomics training |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Training | Managing a mobile team |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Training | ABW workshop |  | Ability |  | Not started | 0% |  |  |  | 1
CM-Sustainability | Provide tours of the modernized workplace |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Sustainability | Create a sustainability committee (to continue the vision) |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Sustainability | Reinforcement communication on new way of working |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Sustainability | Signage (behaviours) |  | Reinforcement |  | Not started | 0% |  |  |  | 1
CM-Sustainability | Signage (how-to) |  | Knowledge |  | Not started | 0% |  |  |  | 1
CM-Sustainability |  |  |  |  | Not started | 0% |  |  |  | 1
CM-Sustainability |  |  |  |  | Not started | 0% |  |  |  | 1
CM-Sustainability |  |  |  |  | Not started | 0% |  |  |  | 1
CM-Sustainability |  |  |  |  | Not started | 0% |  |  |  | 1
CM-Sustainability |  |  |  |  | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1