## Project Timeline
Design System Phase II
Start Date: | 2018-05-10
| sprint 8 |  | sprint 9 |  | sprint 10 |  | sprint 11 |  | sprint 12
| april | may |  |  |  | jun |  |  |  | jul
| wed | wed | thu | wed | thurs | wed | thurs | wed | thurs | wed
Assigned to: | 1900-01-10 | 1900-01-08 | 2018-05-10 | 1900-01-23 | 1900-01-24 | 1900-01-05 | 1900-01-06 | 1900-01-19 | 1900-01-20 | 1900-01-03
Sierra Duffey | project management
| phase I review (implement changes) |  | accessiblity guidelines |  | writing guidelines
| prepare for presentations |  | branding (with SCMA)
Genevieve Lemieux | project management
| phase I review |  | branding (with SCMA)
Thomas Gohard | phase I review |  | accessibility guidelines |  | usability/accessibility testing (in line with development)
Paul Jackson | phase I review |  | accessibility guidelines |  | usability/accessibility testing (in line with development)
Becky Jeong | navigation testing |  |  |  | usability testing (in-line with development)
CLUE student |  |  |  |  | usability testing (in-line with development)
Marianne Aubrey | phase I review (documentation) |  | help material guidelines |  | writing guidelines
Nneka Nnagbo | phase I review (documentation) |  | writing guidelines
Michael Martel | phase I review |  | templates and layouts
Sabrina Rowland-Cote | complete backlog items |  | templates and layouts |  |  |  | phase II components
Chuma Asuzu | complete backlog items |  | templates and layouts |  |  |  | phase II components
Nick Pietrantonio | phase I review (implement changes) |  | coding standards |  | HTML + CSS development
Ethan Wallace | phase I review (implement changes) |  | coding standards |  | HTML + CSS development
Omar Nasr | complete backlog items |  | coding standards |  | HTML + CSS development
Dan Spence | complete backlog items |  | coding standards |  | HTML + CSS development
Stephanie Lefebvre |  |  | coding standards |  | HTML + CSS development