## Planner
GC EARB date: |  | 2022-04-07
Week | Day | DoW | Calcluated dates | Conflict date? | Timeline instructions boilerplate | Timeline instuctions with dates
W-minus-3 | D-minus-20 | Friday | 2022-03-18 |  | – we will require the first draft (English only). | 1. Fri. Mar. 18 – we will require the first draft (English only).
W-minus-2 | D-minus-17 | Monday… | 2022-03-21 |  | – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback | 2. Week of Mon. Mar. 21 – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback
W-minus-2 | D-minus-13 | Friday | 2022-03-25 |  | – updated draft (English only) is collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide. | 3. Fri. Mar. 25 – updated draft (English only) is collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide.
W-minus-1 | D-minus-7 | Thusday | 2022-03-31 |  | – pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck. | 4. Thu. Mar. 31 – pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck.
W-zero | D-minus-3 | Monday | 2022-04-04 |  | – final deck (both English and French) is due for distribution to GC EARB members. (TBS EA will ensure translation of the EA assessment slide.) | 5. Mon. Apr. 04 – final deck (both English and French) is due for distribution to GC EARB members. (TBS EA will ensure translation of the EA assessment slide.)
W-zero | D-zero | Thursday | 2022-04-07 |  | – GC EARB session | 6. Thu. Apr. 07 – GC EARB session
W-plus-1 | D-plus-4 | Monday | 2022-04-11 |  | – meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion | 7. Mon. Apr. 11 – meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion
Copy-pasta of Timeline instuctions with dates (for email send-out)
1. Fri. Mar. 18 – we will require the first draft (English only). 2. Week of Mon. Mar. 21 – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback 3. Fri. Mar. 25 – updated draft (English only) is collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide. 4. Thu. Mar. 31 – pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck. 5. Mon. Apr. 04 – final deck (both English and French) is due for distribution to GC EARB members. (TBS EA will ensure translation of the EA assessment slide.) 6. Thu. Apr. 07 – GC EARB session 7. Mon. Apr. 11 – meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion

## GC EARB dates
GC EARB dates | Conflict dates | Conflict message
2022-03-24 | 2022-01-01 | New Year's Day
2022-04-07 | 2022-04-15 | Good Friday
2022-04-21 | 2022-04-18 | Easter Monday
2022-05-05 | 2022-05-23 | Victoria Day
2022-05-19 | 2022-06-24 | Fete Nationale (SJB)
2022-06-02 | 2022-07-01 | Canada Day
2022-06-16 | 2022-08-01 | August civic holiday
2022-06-30 | 2022-09-04 | Labour Day
2022-07-14 | 2022-09-30 | Truth & Reconcilation Day
2022-07-28
2022-08-11
2022-08-25
2022-09-08
2022-09-22
2022-10-06
2022-10-20
2022-11-03
2022-11-17