## Planner
| Select planned GC EARB date: |  |  | 2022-12-15
Week | Day | DoW | Calcluated dates | Possible Stat Holiday Conflict | Timeline instructions boilerplate | Timeline instuctions with dates
W-minus-3 | D-minus-20 | Friday | 2022-11-25 |  | – First draft (English only) required to be submitted to TBS EA team at EA.AE@tbs-sct.gc.ca. | 1. Fri. Nov. 25 – First draft (English only) required to be submitted to TBS EA team at EA.AE@tbs-sct.gc.ca.
W-minus-2 | D-minus-17 | Monday… | 2022-11-28 |  | – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback | 2. Week of Mon. Nov. 28 – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback
W-minus-2 | D-minus-13 | Friday | 2022-12-02 |  | – Updated draft (English only) is collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide. | 3. Fri. Dec. 02 – Updated draft (English only) is collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide.
W-minus-1 | D-minus-7 | Thusday | 2022-12-08 |  | – Pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck. | 4. Thu. Dec. 08 – Pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck.
W-zero | D-minus-3 | Monday | 2022-12-12 |  | – Final deck (both English and French) is due for distribution to GC EARB members. (TBS EA will ensure translation of the EA assessment slide.) | 5. Mon. Dec. 12 – Final deck (both English and French) is due for distribution to GC EARB members. (TBS EA will ensure translation of the EA assessment slide.)
W-zero | D-zero | Thursday | 2022-12-15 |  | – GC EARB session | 6. Thu. Dec. 15 – GC EARB session
W-plus-1 | D-plus-4 | Monday | 2022-12-19 |  | – Meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion | 7. Mon. Dec. 19 – Meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion
Copy-pasta of Timeline instuctions with dates (for email send-out)
1. Fri. Nov. 25 – First draft (English only) required to be submitted to TBS EA team at EA.AE@tbs-sct.gc.ca. 2. Week of Mon. Nov. 28 – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback 3. Fri. Dec. 02 – Updated draft (English only) is collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide. 4. Thu. Dec. 08 – Pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck. 5. Mon. Dec. 12 – Final deck (both English and French) is due for distribution to GC EARB members. (TBS EA will ensure translation of the EA assessment slide.) 6. Thu. Dec. 15 – GC EARB session 7. Mon. Dec. 19 – Meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion

## GC EARB dates
GC EARB dates | Conflict dates | Conflict message
2022-12-15 | 2022-04-15 | Good Friday
2023-01-19 | 2022-04-18 | Easter Monday
2023-02-02 | 2022-05-23 | Victoria Day
2023-02-16 | 2022-06-24 | Fete Nationale (SJB)
2023-03-02 | 2022-07-01 | Canada Day
2023-03-16 | 2022-08-01 | August civic holiday
2023-03-30 | 2022-09-05 | Labour Day
| 2022-09-30 | Truth & Reconcilation Day
| 2022-10-10 | Thanksgiving
| 2022-11-11 | Remembrance Day
| 2022-12-26 | Christmas Day
| 2022-12-27 | Boxing Day
| 2023-01-02 | New Year's Day