## Project Timeline
Design System Phase II
Start Date: | 2018-05-10
| sprint 8 |  |  | sprint 9 |  | sprint 10 |  | sprint 11 |  | sprint 12
| april |  | may |  |  |  | jun |  |  |  | jul
| wed |  | tues | thurs | wed | thurs | wed | thurs | wed | thurs | wed
Assigned to: | 1900-01-10 |  | 1900-01-14 | 1900-01-16 | 1900-01-29 | 1900-01-30 | 1900-01-12 | 1900-01-13 | 1900-01-26 | 1900-01-27 | 1900-01-10
Sierra Duffey | Away | project management
|  | phase I review |  | accessiblity guidelines |  | writing guidelines
| prepare for Design Talk and Innovation Fair |  |  | branding (with SCMA)
Genevieve Lemieux | project management
| phase I review |  |  | branding (with SCMA)
Thomas Gohard | phase I review |  |  | accessibility guidelines |  | usability testing (staggered with development)
Paul Jackson | phase I review |  |  | accessibility guidelines |  | usability testing (staggered with development)
Becky Jeong | navigation testing |  |  |  |  | template testing |  | usability testing (staggered with development)
CLUE student | [5 empty] | template testing |  | usability testing (staggered with development)
CLUE student | [5 empty] | template testing |  | usability testing (staggered with development)
Marianne Aubrey | phase I review (documentation) |  |  | help material guidelines |  | writing guidelines (tone and messaging)
Nneka Nnagbo | phase I review (documentation) |  |  | writing guidelines (grammar, common terms)
Michael Martel | phase I review |  |  | templates and layouts
branding (with SCMA)
Sabrina Rowland-Cote | backlog items | Away |  | templates and layouts |  |  |  | phase II components
Chuma Asuzu | backlog items |  |  | templates and layouts |  |  |  | phase II components
Nick Pietrantonio | phase I review |  |  | coding standards and setup |  | HTML + CSS development
Ethan Wallace | phase I review |  |  | coding standards and setup |  | HTML + CSS development
Omar Nasr | Away | backlog items |  | coding standards and setup |  | HTML + CSS development
Dan Spence | backlog items |  |  | coding standards and setup |  | HTML + CSS development
Stephanie Lefebvre |  |  |  | coding standards and setup |  | HTML + CSS development