## How to use
HOW TO USE THIS DOCUMENT
This Communication Framework lists all proposed communication activities included in the Implementation phase of the CM Program in-a-box. It can be used by yourself or your communication officer to see all of the activities in one place and get a sense of the sequence. The framework can also help with the implementation of these communication activities.
Validate if the communication activities proposed for this phase are sufficient for your project and if they will answer most of your communication needs. Also validate the last three columns (audience, sender and timing) and consult with all key enablers of the integrated project team (IM, IT, Security, HR, OSH, Facilities) to see if other communication activities might also be required to support specific changes managed in parallel by the enabling sectors. After validation, add/remove communication activities to your CM/PM Plan in the CM Workbook. Note: All proposed activities in this framework are already included in the CM/PM Plan.
We recommend that you use the CM/PM Plan to manage the actual implementation of the communication activities as part of your overall plan.
Do not forget to collect feedback, monitor and evaluate the effectiveness of your communications. Use the CM Activities tracker in the CM Workbook and the CM Monitoring Questionnaire available at the end of Phase II of the Box.

## Framework
Click here to access the French version of this document
Sequence | Activity | Objective | Audience | Sender | Timing, if applicable
1 | Skills and knowledge roadmap announcement | Inform the employees of the resources that have been created for them | Employees | Project sponsor | As early as possible at the start of phase 2, before the People manager's toolkit
2 | Communication to share the People manager's toolkit | Inform the managers of the tool that has been created for them, to help them understand their role in change management for the project. | Managers | Executive sponsor | As early as possible at the start of phase 2, after the Skills and knowledge roadmap announcement
3 | Communication to share the floor plans | Build excitement for employees | Employees | Project sponsor | Once your floorplan is approved
4 | Communication to announce the meeting room naming contest | Build excitement for employees and provide an opportunity to be involved in the project | Employees | Project sponsor | Coordinate with Project team as indicated in Guide
5 | Communication to announce the meeting room naming results | Make employees feel that they participated in this and have a part in the process. | Employees | Project sponsor
6 | Communication to guide managers in inviting employees to the ''A day in the life'' presentation | Make sure managers are ready to inform employees of what the presentation is | Managers | Executive sponsor | 3 weeks before presentation
7 | Outlook invitation for ''A day in the life'' presentation | Invite employees to participate and make sure they know when it is happening by pushing it into their calendar. | Employees | Integrated team | 1 week after sending Communication to guide managers in inviting employees to the ''A day in the life'' presentation, 2 weeks before the presentation
8 | Communication to share the community norms with employees | Inform employees of the community norms established | Employees | Project sponsor
9 | Communication to announce the team charters to managers | Inform managers on how to conduct the activity | Managers | Executive sponsor
10 | Communication to announce the team charters to employees | Inform employees of the activity | Employees | People manager | 1 week after sending Communication to announce the team charters to managers
11 | Pre-opening communication : Opening and employee toolkit announcement | Announce the opening date and share the employee toolkit to give employees all the information they need for the opening | Employees | Project sponsor | 6 weeks before opening day
12 | Pre-opening communication : Hybrid ribbon cutting Outlook invitation | Invite project contributors to participate and make sure they all know when it is happening by pushing it into their calendar. | Project contributors | Project sponsor | 5 weeks before opening day
13 | Pre-opening communication: Guided tour email to managers | Inform managers on how to book their team's guided tour | Managers | Executive sponsor | 4 weeks before opening day
14 | Pre-opening communication : Virtual pre-opening Q&A session Outlook invitation | Invite employees to participate and make sure they know when it is happening by pushing it into their calendar. | Employees | Integrated team | 4 weeks before opening day
15 | Pre-opening communication : Opening reminder | Build excitement and remind employees of the opening date | Employees | Project sponsor | 1 week before opening day
16 | Pre-opening communication : Opening reminder | Build excitement and remind employees of the opening date | Employees | Project sponsor | 1 day before opening day