## About this document
ABOUT THIS DOCUMENT - Edit or remove text in red to suit your needs. Edit the title and the end date in the final column. - Validate all the recommended activities as some may or may not apply to your project. - Add "Actions" or remove column for more high level approach. - Update numbering/lettering to suit. - Adapt the schedule portion on the right to suit your project. The proposed timeline is best suited for projects of one year or less. For longer projects or multi-phase projects, you may wish to remove the weeks and replace them with months, months to quarters, quarters to years, etc.

## PM-CM Integrated Plan (1 yr)
Client departement/Agency–Project name
CHANGE MANAGEMENT APPROACH (adjust cells to suit your timeline) -------------------> | [7 empty] | STRATEGIZE | [14 empty] | PLAN | [14 empty] | IMPLEMENT | [14 empty] | MEASURE
Theme | # | Activity | Action | Start Date | Planned end date | Actual end date | Status | Q1 | [14 empty] | Q2 | [14 empty] | Q3 | [14 empty] | Q4
[8 empty] | April |  |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  |  |  | February |  |  |  |  | March |  |  |  |  | End of Project [insert date]
[8 empty] | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK5
Project management KEY ACTIVITIES |  | 1. Example activity | a. Indicate specific actions for each activity by adding rows, or remove the entire "Actions" column for high level activities only |  |  |  | Not Started | bar: WK4 to WK2
|  |  | b. Indicate planned start and end date on the right |  |  |  | Not Started | bar: WK2 to WK3
|  |  | c. Assign appropriate status from the pulldown menu |  |  |  | Not Started | bar: WK3 to WK4
|  |  | d. Colour the cells in the appropriate year/quarter/month/week to match the colour of the "theme" |  |  |  | Not Started | bar: WK3 to WK3
| 1 | Functional programming |  |  |  |  | Not Started
| 2 | Preliminary space planning |  |  |  |  | Not Started
| 3 | Move to swing space |  |  |  |  | Not Started
| 4 | Design concept |  |  |  |  | Not Started
| 5 | Furniture procurement |  |  |  |  | Not Started
| 6 | Construction |  |  |  |  | Not Started
| 7 | Move |  |  |  |  | Not Started
Change management KEY DELIVERABLES | 8 | Dedicate a CM resource |  |  |  |  | Not Started
| 9 | Project Readiness Assessment |  |  |  |  | Not Started
| 10 | Change Inventory and Impact Assessment |  |  |  |  | Not Started
| 11 | Change Readiness Assessment |  |  |  |  | Not Started
| 12 | ADKAR Change-o-meter questionnaire- quarterly |  |  |  |  | Not Started
| 13 | Stakeholder map |  |  |  |  | Not Started
| 14 | Guide to assessing the sponsor and champions, and Sponsorship assessment tool |  |  |  |  | Not Started
| 15 | Establish teams and committees |  |  |  |  | Not Started
| 16 | CM strategy |  |  |  |  | Not Started
| 17 | Sponsorship roadmap |  |  |  |  | Not Started
| 18 | Change management activity tracker |  |  |  |  | Not Started
| 19 | Workplace performance modernization tracker |  |  |  |  | Not Started
| 20 | Communication plan |  |  |  |  | Not Started
| 21 | Engagement plan |  |  |  |  | Not Started
| 22 | Training plan |  |  |  |  | Not Started
Change management COMMUNICATION | 23 | Kick-off town hall with employees (announce project and vision) |  |  |  |  | Not Started
| 24 | Launch of intranet/newsletter |  |  |  |  | Not Started
| 25 | Quarterly email update |  |  |  |  | Not Started
| 26 | Fact sheets |  |  |  |  | Not Started
| 27 | FAQs |  |  |  |  | Not Started
| 28 | Announce approved floor plans |  |  |  |  | Not Started
| 29 | Announce selected colour scheme |  |  |  |  | Not Started
| 30 | Announce typical furniture layouts |  |  |  |  | Not Started
| 31 | Send initial move information |  |  |  |  | Not Started
| 32 | Send frequent move information |  |  |  |  | Not Started
| 33 | Meet with senior management to inform on project/plan |  |  |  |  | Not Started
| 34 | Visioning session with senior management |  |  |  |  | Not Started
| 35 | Pop-up GCworkplace |  |  |  |  | Not Started
| 36 | Pre-occupancy survey |  |  |  |  | Not Started
Change management ENGAGEMENT | 37 | GCworkplace 101 workshop with employees |  |  |  |  | Not Started
| 38 | Virtual tour of ABW spaces |  |  |  |  | Not Started
| 39 | Functional programming engagement with employees |  |  |  |  | Not Started
| 40 | Launch of live-in program/pilot space |  |  |  |  | Not Started
| 41 | Expert panels |  |  |  |  | Not Started
| 42 | Employee-to-employee panels |  |  |  |  | Not Started
| 43 | Create employee committee (change agents) |  |  |  |  | Not Started
| 44 | Create employee committees (on etiquette) |  |  |  |  | Not Started
| 45 | Employee involvement activities (selection of artwork, room naming, feature wall) |  |  |  |  | Not Started
| 46 | Paper clean-up activity |  |  |  |  | Not Started
Change management TRAINING | 47 | One pagers |  |  |  |  | Not Started
| 48 | GCdocs refresher course |  |  |  |  | Not Started
| 49 | Clean desk refresher course |  |  |  |  | Not Started
| 50 | Mobile device training |  |  |  |  | Not Started
| 51 | New application training |  |  |  |  | Not Started
| 52 | New ways of working session |  |  |  |  | Not Started
| 53 | Office ergonomics training |  |  |  |  | Not Started
| 54 | Managing a mobile team |  |  |  |  | Not Started
| 55 | Leadership Toolkit |  |  |  |  | Not Started
| 56 | Manager Toolkit |  |  |  |  | Not Started
| 57 | Change agent Toolkit |  |  |  |  | Not Started
| 58 | ABW workshop for employees |  |  |  |  | Not Started
Change management CLOSE-OUT | 59 | Post-occupancy survey |  |  |  |  | Not Started
| 60 | Evaluate the activities implemented and make necessary adjustments |  |  |  |  | Not started
| 61 | Change management activity tracker |  |  |  |  | Not Started
| 62 | Workplace performance modernization tracker |  |  |  |  | Not Started
| 63 | Monitor employee adoption |  |  |  |  | Not Started
| 64 | Sustain the change by reinforcing new behaviors, and addressing gaps and resistance |  |  |  |  | Not started
| 65 | Celebration |  |  |  |  | Not Started