## Slide 1: Change Management Strategy
Template
VERSION 2
May 2023

## Slide 2: How to use this document
To use this template, we highly recommend that you complete the first 3 tabs of the CM Workbook:
  PRET form (Change Readiness Section)
  Change Inventory and Impact Assessment
  Contributors Table
The results from these 3 assessment documents will provide you with some insights that will help you to transform this predesigned CM strategy into a strategy that will be adapted to your organization’s needs.
Throughout this document, there is guidance and recommendations highlighted in yellow on how to adapt each page.
Instructions – Remove this page before use

## Slide 3: Context: Organizational and Project Vision
Include the vision developed in collaboration with the PSPC Strategic Workplace Advisory Group (SWAG) and approved by your senior leadership
After working from home for the last two years, it is now time to look to the future and plan our return to the workplace.
[Organization] will be taking part in the workplace transformation program, which aims to provide a department wide modernized workplace that will support all employees in a new hybrid work model.
The space at [Location] will be designed to foster a culture of innovation and improving digital technology to encourage government wide collaboration, flexibility and efficiency. It will also integrate sustainability and improve the overall health and well-being of employees and ensuring inclusivity for all.
As a starting point for our hybrid model, employees will be given the choice to work from the office based on operational requirements, functions or personal preferences. With flexibility in mind, this working model may evolve over time based on employee feedback.
We will continue to adapt and offer support to all employees during the course of this modernization project. Together our contributions help shape the future of our organization!
EXAMPLE

## Slide 4: Context: Project Management Readiness
These are the 4 Project Management Readiness statements included in the PRET. If these are true for your organization, include them here as context. If the statements are somewhat or not in line with the reality at your organization, include them on the Risks and considerations slide.
Our organization's workplace strategy is being supported by a project sponsor that can be active and visible throughout the entire project. The project sponsor has the necessary authority over the people, processes, and systems to authorize and fund the necessary changes.
Our organization's leaders have made workplace modernization a priority. Leaders are ready to communicate this change in the context of other competing priorities and are willing to walk the talk.
Our organization has developed a workplace modernization strategy and has the necessary resources to implement the strategy, including project champions, a project integrator and subject matter experts.
Our organization has a structured change management approach for the project and has identified trained resources for change management. Resources are available to provide communication advice, develop communications products and provide training to employees.

## Slide 5: Context: Change Readiness
These are the 4 Change Readiness statements included in the PRET. If these are true for your organization, include them here as context. If the statements are somewhat or not in line with the reality of your organization, include them on the Risks and considerations slide.
Our organization's history of change is successful, employees have embraced the past changes and did not revert back to old ways.
Our organization is open to new ideas and innovation, employees are rewarded for risk taking and embracing change.
Senior leaders and managers in our organization are highly skilled at managing change, performance is evaluated based on results and not based on employees’ presence.
Employees in our organization are encouraged, trusted and empowered to make choices about when, where and how they work based on what makes sense. Remote work (i.e. telework) is supported with policies, agreements and/or other mechanisms.

## Slide 6: Change Management Strategy Objectives
Inform, involve and equip impacted employees towards the change and reinforce new mindsets and behaviours for the future.
  Ensure employees feel informed and supported while the change is occurring, demonstrating the need for change, the impacts and the benefits the new ways of working will have on their daily work activities.
  Build desire among people managers, senior leaders and all employees to actively participate in the change impacting their workplace, to develop a sense of ownership that will ensure a new mindset and behaviours are sustained.
  Equip employees with the necessary resources, training and guides on how to change the way they work and their behaviours, to ensure they are confident to perform to work efficiently and productively in the new space.
  Reinforce the change through people managers and senior leaders, to ensure employees adopt and sustain the new mindset and behaviours.
[OPTIONAL] Add additional objective(s) based on Readiness Assessments and outcomes of the CM Kick-off Session.

## Slide 7: Objective 1 - Inform
If you are presenting your strategy to a senior audience, we recommend not including the next 4 slides as the information presented is too detailed. You can use Slide 13 High-Level CM Plan as an overview for that audience.
Ensure employees feel informed and supported while the change is occurring, demonstrating the need for change, the impacts and the benefits the new ways of working will have on their daily work activities.
  Announcements from the project sponsor
    Project announcement
    Floor plan announcement
    Pre-opening announcements
  Communication channel(s) and content (intranet, newsletter and/or MS Teams channel)
    Commonly asked questions
    Key messages
    PSPC Project Story Collection
  Direct communication from people manager to employees
    Manager toolkit

## Slide 8: Objective 2 - Involve
Build desire among managers, executives and all employees to actively participate in the change impacting their workplace, to develop a sense of ownership that will ensure a new mindset and behaviours are sustained.
  Townhalls and events
    Project announcement townhall
    Pre-opening townhall
    Tour of the new workspace
    Hybrid opening ceremony
  Project engagement activities
    Design survey
    Removal of personal & business assets
    Boardroom naming
  New ways of working
    Community norms (etiquette)
    Team charters
  Change Agent Network

## Slide 9: Objective 3 - Equip
Equip employees with the necessary resources, training and tools on how to change the way they work and their behaviours, to ensure they are confident to perform to work efficiently and productively in the new space.
  Toolkits/User guides
    Managers
    Employees
  Training
    Guides and tutorials
    A day in the life presentation
    Training content

## Slide 10: Objective 4 - Reinforce
Reinforce the change through managers and executives, to ensure employees adopt and sustain the new mindset and behaviours.
  Communication from Project Sponsor
    Change sustainment communiques
    Workplace performance survey
  Direct communication from manager to employees
    Manager toolkit

## Slide 11: Risks and considerations (1 of 2)
Add any of the Project Management Readiness Assessment and Change Readiness statements that are somewhat or not in line with the reality at your organization. Add a small paragraph on how you plan to address the condition(s).
EXAMPLE: Leaders are somewhat ready to communicate this change in the context of other competing priorities and are somewhat willing to walk the talk. In order to ensure our senior leaders are well equipped to manage this change, we will host a mandatory 1h session on how to manage change where the project sponsor will reiterate the priority of this initiative and its success. We will also provide a Leadership toolkit that contains relevant resources to equip the senior leaders. [include additional details as to how you will go about doing this]
Add any consideration relating to Contributors:
  List any Resister groups and their challenges and barriers. Add a small paragraph on how you plan to address the condition(s).
  EXAMPLE: Employees from Branch XYZ have shown resistance to the new workplace as the floor being renovated used to be ‘their’ floor and they are not please that it will now be shared with the entire organization. We will equip the managers and senior leaders of the Branch to reinforce key messages such as the ‘Why’ for the change and the ‘What’s in it for me’ for employees. Additional information sessions, question and answer periods as well as Ask Me Anything sessions with senior leaders will be scheduled. [include additional details as to how you will go about doing this]
  List any Enthusiast groups with their opportunities. Add a small paragraph on how you plan to use these groups to help in your strategy.
  EXAMPLE: Our organization has been actively engaging with our union(s) and they are strong supporters of the new workplace as it will provide flexibility for employees who choose to work from the office. As such, we will work with the union(s) and their employee representatives to communicate key elements for the new workplace directly to employees. [include additional details as to how you will go about doing this]
Complete this section based on the results of the Readiness assessments in the PRET and Contributors table in the CM Workbook, as well as the outcome of the CM Kick-off Session.

## Slide 12: Risks and considerations (2 of 2)
Add any Client enabling initiatives in the Change inventory and impacts that have a High/Medium impact that have specific conditions that need to be addressed as part of your strategy.
  EXAMPLE: The creation of a new interim/telework agreement has taken longer than anticipated. As a result, questions about this are being asked at all our engagements regarding the Workplace Transformation Project. Employees are concerned and confused as to what the future of hybrid will look like in our organization and therefore have a risk of becoming resistant. To address this, we will work with the HR representative on our Integrated project team to see if more frequent communication on the interim/telework agreement can be shared with employees. [include additional details as to how you will go about doing this]
Complete this section based on the results of the Readiness assessments in the PRET and Contributors table in the CM Workbook, as well as the outcome of the CM Kick-off Session.

## Slide 13: High-Level Change Management Plan
Present here a high-level CM plan. You can use the Content overview included in the CM Program in-a-box (as shown below) or your own timeline.
Access the most recent version here : https://wiki.gccollab.ca/images/3/39/WTP_-_CM_Program_in-a-box_EN.pdf
If you would like to obtain an editable version, please contact the Workplace Change Management National Centre of Expertise.

## Slide 14: Expected outcomes
Inform
  Employees are well informed of the changes that will take place in their workplace
  Employees understand the reasons for the upcoming changes to their workplace
  Employees understand the impact of the upcoming changes to their workplace on their day-to-day work activities
Involve
  People managers, senior leaders and all employees are motivated to be part of the change in their workplace
  People managers, senior leaders and all employees look forward to the changes to their workplace
  Employees feel people managers support the change
  Employees feel senior leaders support the change
Equip
  Employees know where to go to get information on the upcoming changes to their workplace
  Employees have the knowledge to be successful in their new work environment
  Employees are confident they will be able to perform their activities effectively in their future work environment
  Employees have access to resources (training/people) to acquire the ability to work effectively in their new work environment
Reinforce
  Employees feel the organization is supporting its employees to work in a mobile way
  Senior leaders are supportive of new ways of working
  People managers are supportive of new ways of working
[OPTIONAL] If you added additional objective(s) on the Objectives slide, be sure to include their expected outcomes here.

## Slide 15: Change inventory and impact assessment
Include the results of your Change inventory and impact assessment
EXAMPLE
REPLACE WITH A PICTURE OF YOUR CHANGE INVENTORY AND IMPACT ASSESSMENT RESULTS

## Slide 16: Contributors table
Include the results of your Contributors table
EXAMPLE
REPLACE WITH A PICTURE OF YOUR CONTRIBUTORS TABLE RESULTS