## DND
Service Line Application | ECD CM Number | DND RFC (Infrastructure) | DND RFC (Application) | DND CFSR | Description | Asset Category | Model/Part Number | Pre-RFC Design Document | DND Intimation by Date | RFC Intialize Due Date | Status | RFC Approval Target Date | Move Target Date | MAC FORM (Equipment) | DMP link | Contacts (DND/SSC) | Email | Additional Email
Infrastructure Master RFC | CM10024321 | 49293 |  |  | Master RFC for WLM DND |  |  |  |  | 2020-09-27 | Chng Approved | 2020-11-26
Migration Parent RFC |  |  |  |  | Master Migration Parent RFC |  |  |  |  | 2021-01-06 | Not Started | 2021-02-02
SISD |  |  |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  |  |  | 2020-11-23 | Pre-RFC DND Review Ongoing | 2020-12-18
SISD |  |  |  |  | Pre RFC Design Document - Network WAN |  |  |  |  | 2020-11-30 | Pre-RFC DND Review Ongoing | 2020-12-18
SISD |  |  |  |  | Pre RFC Design Document - SAN Storage |  |  |  |  | 2020-12-09 | Tkt In Draft | 2020-12-18
SISD |  |  |  |  | Pre RFC Design Document - Misc Security Services |  |  |  |  | 2020-12-18 | Tkt In Draft
SISD |  |  |  |  | Pre RFC Design Document - Virtualization Infrastructure |  |  |  |  | 2020-12-18 | Tkt In Draft
SISD |  |  |  |  | Pre RFC Design Document - WinCore |  |  |  |  | 2020-12-18 | Tkt In Draft
Storage | CM10023978 |  |  |  | ECD RFC - New GPNET Hitachi G700 Disk Array GPNET SAN array & switches VSP G700 Base G620, 48-port, 48x32G optics, Ent Bdl,Portside exh | Storage | G700-BASE.P G620 | Pre RFC Design Document - SAN Storage |  | November 19 2020 | Chng Approved | 2020-12-09 |  | https://gcdocs.gc.ca/ssc-spc/llisapi.dll?func=ll&objid=68987637&objAction=browse&sort=name&viewType=1 |  | Kate Condon | kate.condon@canada.ca
Storage | CM10023977 |  |  |  | CFRS TDC - G700 Disk Array |  |  | Pre RFC Design Document - SAN Storage |  | TBD | Chng Tkt Initialized | TBD |  | https://gcdocs.gc.ca/ssc-spc/llisapi.dll?func=ll&objid=68987637&objAction=browse&sort=name&viewType=1
Storage |  |  |  |  | TDC Fabric Switches |  |  | Pre RFC Design Document - SAN Storage |  | February 3 2021 | Not Started | 2021-02-23 |  | Require MAC form
Storage |  |  |  |  | TDC – Install G700 Array |  |  | Pre RFC Design Document - SAN Storage |  | February 3 2021 | Not Started | 2021-02-23
Storage |  |  |  |  | TDC – Install HNAS |  |  | Pre RFC Design Document - SAN Storage |  | February 3 2021 | Not Started | 2021-02-23
Storage |  |  |  |  | TDC – Install Management Server |  |  | Pre RFC Design Document - SAN Storage |  | February 3 2021 | Not Started | 2021-02-23
Storage |  |  |  |  | DND Child RFC (FCIP switch connections to Nexus) include racking/cabling |  |  | Pre RFC Design Document - SAN Storage |  | February 2 2020 | Not Started | 2020-02-22
Storage | CM10034163 |  |  |  | ECD RFC Production – Install VSP5100 Storage Array |  |  | Pre RFC Design Document - SAN Storage |  | 2020-12-07 | Chng TkT in System | 2021-01-08
Storage | CM10034239 |  |  |  | ECD RFC Production – Install VSP5500 Storage Array |  |  | Pre RFC Design Document - SAN Storage |  | 2020-12-07 | Chng TkT in System | 2021-01-08
Storage |  | 50467 |  |  | DND Child RFC Gpnet Fabric extension Switches (Tun) /Connectivity |  |  | Pre RFC Design Document - SAN Storage |  | 2021-01-11 | Tkt In Draft | 2021-02-01 |  | Require MAC form
Storage |  |  |  |  | ECD RFC for Connectivity approved (Borden) |  |  | Pre RFC Design Document - SAN Storage |  | 2020-12-03 |  | 2021-01-06
Storage |  |  |  |  | EDC RFC For MCSC |  |  | Pre RFC Design Document - SAN Storage
Storage |  |  |  |  | DND RFC For MCSC |  |  | Pre RFC Design Document - SAN Storage
Security OPS |  |  |  |  | ECD RFC for CITS Management |  |  |  |  | 2021-02-16 | Not Started | 2021-03-08
Security OPS |  |  |  |  | ECD RFC for CHSS -Aruba-CP (Chris) - depends on CITS mngt |  |  |  |  | 2021-02-16 | Not Started | 2021-03-08
Security OPS |  |  |  |  | ECD RFC for iAccess (Stephane) |  |  |  |  | 2021-02-16 | Not Started | 2021-03-08
ECD RFC for iAccess (Stephane)
Security OPS |  |  |  |  | ECD RFC for Remote Access |  |  |  |  | 2021-02-16 | Not Started | 2021-03-08
ECD RFC for Remote Access
Security OPS |  |  |  |  | ECD RFC for DIG |  |  |  |  | 2021-02-16 | Not Started | 2021-03-08
Security OPS |  |  |  |  | ECD RFC for DRMIS Firewalls |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  | 2021-04-08 | Not Started | 2021-04-21
Security OPS |  |  |  |  | ECD RFC for PERMIS Firewalls |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  | 2021-04-08 | Not Started | 2021-04-21
Network WAN | CM10024053 |  |  |  | Installation of DELL EMC Data Domain 6300 with one expansion shelf in Borden Data center . The Data Domain will be used for TDC environment being setup in Borden as part of WLM Data Domain Disk Drive | Backup | DD6300 DD6300 DS60 expansion Shelf | Pre RFC Design Document - Network WAN |  | TBD | Chng Cancelled (see notes) | TBD |  | https://gcdocs.gc.ca/ssc-spc/llisapi.dll?func=ll&objid=68987637&objAction=browse&sort=name&viewType=1 |  | Gervais Iyamuremye | gervais.iyamuremye@ssc-spc.gc.ca
Network WAN |  |  |  |  | WAN cutover (*DCN change process also automatically creates DND CFSRs when required, which it will be in this case) |  |  | Pre RFC Design Document - Network WAN |  | TBD | Not Started | TBD
Network WAN |  |  |  |  | Develop RFCs (infoMan, ECD) |  |  | Pre RFC Design Document - Network WAN |  | Feb 08, 2021 | Not Started | 2021-03-03
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC Borden |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC LS2 |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC 400 Cumberland |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC SHI |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC PEARKES (DWAN) |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC PEARKES (DRENET) |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC TUN |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network WAN |  |  |  |  | Prep work (DND Child RFC & SSC InfoMan RFC HDV |  |  | Pre RFC Design Document - Network WAN |  | 2021-01-25 | Not Started | 2021-02-12
Network DCN | CM10032647 |  |  |  | DCN Infrastructure Installation and Cabling – MAC form 1 (will be submitted Friday Oct 23). MAC submitted Nov 03. | Network | Cisco NCS2K EMC Connectrix MP-7840B HITACHI G700 Brocade G620 Cisco N77-C7706 Cisco N9K-C93180YC-FX2 Cisco N9K-C9336C-FX2 Cisco APIC-L3 | Pre RFC Design Document - Network DCN + Security Perimeter |  | 2020-02-05 | Completed | TBD | 2020-11-18 | MAC-DCN WLM CORE1A Form: https://gcdocs.gc.ca/ssc-spc/llisapi.dll/open/68987628 |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  |  |  |  | DCN Infrastructure Installation and Cabling – MAC form 1 (will be submitted Friday Oct 23) |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Chng Tkt Outstanding |  |  | Require MAC form 1 |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  |  |  |  | DCN Infrastructure Installation and Cabling - MAC form 2 |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Chng Tkt Outstanding |  |  | Require MAC form 2 |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  |  |  |  | DCN Firewalls Installation and Cabling |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Not Started |  |  |  |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  |  |  |  | WAN cutover (*DCN change process also automatically creates DND CFSRs when required, which it will be in this case) |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Not Started |  |  |  |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  |  |  |  | Post Migration LAN extension disconnect (* same note as above) |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Not Started |  |  |  |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  | 50401 |  |  | DND RFC TDC DCN Implementation – including stretched VLANs from Tunney’s (technically not really needed, but we’ll just do it anyways to avoid any issues) TDC WAN firewall DCN will do an RFC which will incorporate some of the security components as DCN and Security team will be jointly installing and configuring gear that affects the boundary SMN Temporary subnet for building fabric |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  | 2020-11-19 | Tkt Complete-Ready for DND Review |  |  |  |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN | CM10034654 | 50021 |  |  | DND RFC DWAN/GPNET Capacity Addition (already completed and ready in draft mode – 50021) |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Chng TkT in System |  |  |  |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  | 50426 |  |  | DND RFC SMN extension | Security |  | Pre RFC Design Document - Network DCN + Security Perimeter |  | 2020-11-06 | Tkt Complete-Ready for DND Review |  |  |  |  | Salman Naqvi | salman.naqvi@canada.ca
Network DCN |  |  |  |  | DND RFC DND DCN Network visibility/monitoring |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Not Started | 2020-11-13
?Network Optical | CM10034729 |  |  | CFSR# R3219530 | CFSR APPROVEDRelated to CM10024321: EDC Borden WLM Migration: Connect DND to Optical Network
Network Optical | CM10032542 |  |  |  | Montreal: Optical card implementation (in Mltr): 90% (CM10032542, WO11882630) | Network | TBD | Pre RFC Design Document - Network DCN + Security Perimeter |  |  | Chng Execution | 2020-11-19
Network Optical | CM10032542 |  |  |  | Dorval: Optical card implementation (in Dorval): 0% (Pending) (CM10032542, WO11885071) | Network | TBD | Pre RFC Design Document - Network DCN + Security Perimeter
Linux/UNIX |  |  |  |  | ECD RFC (Sparc) Move TDC SPARC servers |  |  | Pre RFC Design Document - LUOps |  | March 16 2020 | Not Started | 2021-04-14
Linux/UNIX |  |  |  |  | ECD RFC (Building the Power Series) Lifecycle the IBM Power series system |  |  | Pre RFC Design Document - LUOps |  | March 16 2020 | Not Started | 2021-04-14
Linux/UNIX |  |  |  |  | ECD RFC (Migration of LPARs) Migrate LPARs to P9 CFSR? |  |  | Pre RFC Design Document - LUOps |  | 2021-03-16 | Not Started | 2021-04-14
Not Started
Virtualization |  |  |  |  | ECD RFC Lift and shift 2 of the 4 enclosures and then lift and shift the remaining 2 enclosures? |  |  | Pre RFC Design Document - Virtualization Infrastructure |  | May 7 2021 |  | 2021-05-07
Virtualization |  |  |  |  | ECD RFC TDC PB & TDC DIG enclosure in TDC? |  |  | Pre RFC Design Document - Virtualization Infrastructure |  | April 23 2021 |  | 2021-04-26
Virtualization |  |  |  |  | DND RFC Create DND RFC to install vSphere on servers for Consolidated PB. (Linked to line 136 Create ECD RFC and Mac to install 4 new PB Blades into PB Chassis in DCB) | Virtualization |  | Pre RFC Design Document - Virtualization Infrastructure |  | TBD | Not Started | TBD |  |  |  | Leonard Sherrer | leonard.sherrer@ssc-spc.gc.ca
Virtualization |  |  |  |  | DND RFC Create DND RFC to install vSphere on servers and create vCenter Server for GPNet. (Linked to line 138 Create ECD RFC and Mac to install 4 new GPNET Blades into Dig Chassis) | Virtualization |  | Pre RFC Design Document - Virtualization Infrastructure |  | 2021-01-07 | Not Started | 2021-01-27 |  |  |  | Neil
Virtualization |  |  |  |  | DND RFC CFSR - GPNet Hosting Env (vSphere ESXi and creating a new vCenter) |  |  | Pre RFC Design Document - Virtualization Infrastructure |  | 2021-01-29 |  | 2021-01-29
Virtualization |  |  |  |  | DND RFC Create DND RFC to install vSphere on servers for DRDC ((If we need to install more blades in the DRDC enclosure to expand that hosting environment, then we will need to submit a RFC to install vSphere ESXi on those blades. Again the Win Ops Team will need to submit a RFC to cover the installation of the blades. Leonard/Neil: Are we waiting for Murray’s DD to confirm ? We are still finalizing DRDC inventories and then what compute can be virtualized and what can’t. Then we have to determine the resources required for each VM and then see if the hosting environment will need to be expanded.)) | (DRDC) |  | Pre RFC Design Document - Virtualization Infrastructure |  | TBD | Not Started | TBD |  |  |  | Leonard/Neil | Leonard.Sherrer@ssc-spc.gc.ca | neil.weller@ssc-spc.gc.ca
WINOPS |  |  |  |  | HDV requires 4 RFC - to follow up | [10 empty] | Stephanie Houle
WINOPS |  |  |  |  | DND RFC to migrate Print services to LS2 |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | DND RFC to migrate files services to new virtual cluster in LS2 |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | DND RFC to Decommission or Relocate SCCM server |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | DND RFC to Decommission DC |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift |  |  | Pre RFC Design Document - WinCore |  | February 9 2021 | Not Started | 2021-02-09
WINOPS |  |  |  |  | Cumberland requires 4 RFC
WINOPS |  |  |  |  | DND RFC to migrate Print services to LS2 |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | DND RFC to migrate files services to new virtual cluster in LS2 |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | DND RFC to Decommission or Relocate SCCM server |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | DND RFC to Decommission DC DWAN |  |  | Pre RFC Design Document - WinCore |  | January 28 2021 | Not Started | 2021-02-17
WINOPS |  |  |  |  | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift |  |  | Pre RFC Design Document - WinCore |  | February 9 2021 | Not Started | 2021-02-09
WINOPS |  |  |  |  | PRK (DWAN only)
WINOPS |  |  |  |  | DND RFC to migrate Print services to LS2 - PRK (DWAN) |  |  | Pre RFC Design Document - WinCore |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | DND RFC to migrate files services to new virtual cluster in LS2 |  |  | Pre RFC Design Document - WinCore |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | DND RFC to Decommission or Relocate SCCM server |  |  | Pre RFC Design Document - WinCore |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | DND RFC to Decommission DC, Old Backup Server and Terminal sever DWAN |  |  | Pre RFC Design Document - WinCore |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | EIS-OCN-AP02224 Volicon unsure what will happen with this |  |  |  |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | EIS-OCN-AP02225 Volicon unsure what will happen with this |  |  |  |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | EIS-OCN-AP02226 Volicon unsure what will happen with this |  |  |  |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | EIS-OCN-AP02227 Volicon unsure what will happen with this |  |  |  |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | EIS-PRK-AP03907 ICE Call system Will not move and must remain Physical |  |  |  |  | March 31 2021 | Not Started | 2021-03-31
WINOPS |  |  |  |  | EIS-PRK-QP03908 ICE Call system Will not move and must remain Physical |  |  |  |  | March 31 2021 | Not Started | 2021-03-31
[5 empty] | DND to raise CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift |  |  |  |  | April 21 2021 | Not Started | 2021-04-06
WINOPS |  |  |  |  | PRK (NCRNET only Child domain for GPNET)
WINOPS |  |  |  |  | DND RFC Create DND RFC - File server |  |  | Pre RFC Design Document - WinCore |  | 2021-03-18 | Not Started | 2021-03-31
WINOPS |  |  |  |  | DND RFC DC NCRNET (this is a child domain of GPNET- where all the workstations sit) |  |  | Pre RFC Design Document - WinCore |  | 2021-03-19 | Not Started | 2021-03-31
WINOPS |  |  |  |  | DND RFC SSCM (Exception requested-patching all client workstations) |  |  | Pre RFC Design Document - WinCore |  | 2021-03-20 | Not Started | 2021-03-31
[5 empty] | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift |  |  |  |  | 2021-03-23 |  | 2021-03-30
WINOPS |  |  |  |  | PRK (CORA + CORP only - To be rewied with Amir) |  |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | NCR-VCW is the Remote desktop system | WinOps Core |  | Pre RFC Design Document - WinCore |  | March 29 2021 | Not Started | 2021-03-29
WINOPS |  |  |  |  | COR-EMAIL1 unknow at this time | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | COR-EMAIL2 unknow at this time | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | CRP-EMAIL1 unknow at this time | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | CRP-EMAIL2 unknow at this time | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to create new 7 VM for COR and CRP application in DCB -PRK (CORA + CORP) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to create new VM for COR DC in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to create new VM for CRP DC in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | ECD RFC and MAC to Standup new physical COR DC in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | ECD RFC and MAC to Standup new physical CRP DC in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to migrate Cor Print services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to migrate Cor files services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to migrate CRP Print services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to migrate CRP files services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to Decommission or Relocate SCCM server | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | ECD RFC and Mac to relocate Backup Server to DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | DND RFC to Decommission CRP-VS1 and CRP-VS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | ECD RFC and MAC to relocate HPC Chassis and Blades | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-04-12 |  | 2021-03-29
WINOPS |  |  |  |  | Note: DND will need to Create a RFC for 11 Virtual workstation | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-29 | Not Started | 2021-03-29
WINOPS |  |  |  |  | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift | WinOps |  | Pre RFC Design Document - WinCore |  | 2021-04-12 |  | 2021-04-12 |  |  |  | Michael H.
WINOPS |  |  |  |  | DRDC Shirley`s Bay (File Server cluster lift and Shift) |  |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | Submit ECD RFC | WinOps |  | Pre RFC Design Document - WinCore |  | 2021-03-29 |  | 2021-03-29 |  |  |  | Michael H.
WINOPS |  |  |  |  | Shirley`s Bay(DRENET only) |  |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | DND RFC to Decommission OTT-V-Library OTT-V-Library2 |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started | 2021-04-06
WINOPS |  |  |  |  | ECD RFC and Mac to migrate backup server to DCB EIS-OTT-BP06839 |  |  | Pre RFC Design Document - WinCore |  | 2021-04-09 | Not Started | 2021-04-09
WINOPS |  |  |  |  | ECD RFC and Mac to install new backup server to DCB Ent-btopaz |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | DND RFC to create new 2 VM for ENT-COPAL and ENT-czizcon DC in DCB |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | ECD RFC and MAC to Standup new DC in DCB for ENT-Cpyrite |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | ECD RFC and MAC to Standup new DC in DCB for OTT-C-LIGHTNING |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | DND RFC to create new 7 VM for application in DCB |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac for the installation of 4 new physical server in DCB |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | OTT-A-APPS1, OTT-A-SIA, OTT-A-TWISTER64, Sandstorm |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | DND RFC and Mac to migrate file servers to LS2 EIS-SHI-PP07264 EIS-SHI-PP07263 |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to migrate to DCB EIS-SHI-TP07691 New Gon |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | DND RFC to Decommission EEWV-RM19, ENT-Vslate, Ent-Vquartz, ENT-VDiamond, OTT-B-BLIZZARD |  |  | Pre RFC Design Document - WinCore |  | 2021-04-06 | Not Started
WINOPS |  |  |  |  | Unknown as this is a SCCM server. BR25094 to upgrade DRDC SCCM is in Design Phase |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | OTT-M-SCCM |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | Unknown as these are Exchange servers. Exchange Team is working on upgrade/redesign. |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | OTT-E-EXCHANGE2 |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | OTT-E-EXCHANGE1 |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | Ent-Ebes |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | ENT-EEMERALD |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | ENT-ERUBY |  |  | Pre RFC Design Document - WinCore |  | TBD
WINOPS |  |  |  |  | Shirley`s Bay(DWAN only) |  |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | DND RFC to migrate Print services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | Maech 29, 2021 | Not Started
WINOPS |  |  |  |  | DND RFC to migrate files services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | Maech 29, 2021 | Not Started
WINOPS |  |  |  |  | DND RFC to Decommission or Relocate SCCM server | WinOps Core |  | Pre RFC Design Document - WinCore |  | Maech 29, 2021 | Not Started
WINOPS |  |  |  |  | DND RFC to Decommission DC | WinOps Core |  | Pre RFC Design Document - WinCore |  | Maech 29, 2021 | Not Started
[5 empty] | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift | WinOps Core |  |  |  | 2021-04-16
WINOPS |  |  |  |  | Tunneys OEA |  |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | ECD RFC and Mac to replace both Dig Chassis in DCB (one at a time) | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to replace both PB Chassis in DCB (one at a time) | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to install 4 new PB Blades into PB Chassis in DCB - linked to line 55 Create DND RFC to install vSphere on servers for Consolidated PB. Linked to line 136 | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to move first GPNET DC to DCB (need rack space location) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to install 4 new GPNET Blades into Dig Chassis - linked to line 56 (Create DND RFC to install vSphere on servers and create vCenter Server for GPNet.) | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to move new GPNET Backup server to DCB (need rack space location) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to move last GPNET DC to DCB (need rack space location) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | DND RFC and Mac to decommission old GPNET chassis and blades (after the system is in DCB) | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | DND RFC and Mac to Decommission old 2008 Backup server (30 days after new backups are running in DCB) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | DND RFC and Mac to Decommission old 2008 servers in OEA (these are servers no longer need) - Ask Michael | Not WLM ?? |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Tunneys 3RD Floor (on hold - WinOps need to review) | Michael H |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | Create DND RFC to migrate DWAN Print services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC to migrate DWAN files services to LS2 | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC and Mac to Decommission old DWAN 2008 Backup server (30 days after new backups are running in LS2) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC and Mac to Decommission or relocate DWAN DC | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC and Mac to Decommission NCRNET DC (after it has been moved to DCB) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC and Mac to Decommission NCRNET File Server (after it has been moved to LS2) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC and Mac to decommission old NCRNET DHCP (after the DHCP scope are moved to LS2) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Create DND RFC and Mac to decommission old NCRNET exchange (after the exchange has moved to DCB) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
Copying over and cutover at Tunneys 3RD Floor
[5 empty] | CFSR for service outage (DIMEUS 7-3) - Depend on WAN uplift |  |  |  |  | 2020-04-14
WINOPS |  |  |  |  | Tunneys TDC (On Hold - might be covered by the DCN WAN design RFC submitted by Ed - still need these for Borden) |  |  | Pre RFC Design Document - WinCore
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate 4 TDC Chassis in DCB (one at a time) | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate PB Chassis in DCB (this will require an outage to both TDC DIG and TDCPB) | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate VM Sandbox Chassis in DCB | WinOps/Vsphere |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate old exchange Chassis in DCB (this will require an outage for the exchange testing) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate 6 Physical exchange servers in DCB (move 3 at a time) | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate 3 Physical SCCM servers in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate 4 Physical Backup servers in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | ECD RFC and Mac to Migrate 2 Physical Managment servers in DCB | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
WINOPS |  |  |  |  | Unsure at this time how many more we may need. But this is the major equipment we need to take care of | WinOps Core |  | Pre RFC Design Document - WinCore |  | 2021-03-22 | Not Started
Network LAN |  |  |  |  | Post Migration LAN extension disconnect (* DCN change process also automatically creates DND CFSRs when required, which it will be in this case) |  |  | Pre RFC Design Document - Network DCN + Security Perimeter |  | TBD | Not Started | TBD |  |  |  | Salman Navqi
Backup |  |  |  |  | RFC 1: Install a new DD6300 in Borden for DRDC "CORA", and migrate CORA *and* Root AD Domain from the NCR to Borden. That DD has been delivered to Wills Warehouse, waiting for the right time to deliver (not scheduled yet) | (DRDC) |  |  |  | TBD | Not Started | TBD
Backup |  |  |  |  | RFC 2: Install a new DD6300 in Borden for DRDC "OTTAWA", and migrate CORA That DD has been delivered to Wills Warehouse, waiting for the right time to deliver (not scheduled yet) | (DRDC) |  |  |  | TBD | Not Started | TBD
Backup |  |  |  |  | (As CHANGE 1 and CHANGE 2 completes, we'll start migrating CORA and OTTAWA clients to Borden. As each environment finally leaves NCR, we can proceed to CHANGE 3 and CHANGE 4 as applicable) RFC 3: Old DRDC "CORA" DD6300 will move to Borden, and be reused to backup NOC | (DRDC) |  |  |  | TBD | Not Started | TBD
Backup |  |  |  |  | RFC 4: Old DRDC "OTTAWA" DD9300 will move from Shirleys Bay to LSL2, and be reused to support the DRDC LSL2 F&P Cluster. | (DRDC) |  |  |  | TBD | Not Started | TBD
Backup | CM10024321 |  |  |  | GPNet BACKUP ECD RFC 5 Install new DD6300 in Borden as GPNet, Migrate GPNet, Move old DD6300 to Wills Warehouse, for possible redeployment later |  |  |  |  | 2020-10-30 | Chng Approved | 2020-11-20
Backup | CM10024053 |  |  |  | TDC BACKUP ECD RFC 6 - Install new DD6300 in Borden for TDC. There is a brand new DD purchased for TDC in Borden. Old TDC Backup storage will be moved to Wills Warehouse, for possible redeployment later. |  |  |  |  | 2021-02-23 | Chng Cancelled (see notes) | 2021-03-15
Backup | CM10034981 | 50469 |  | CFSR R3234979 | DND RFC Installation of new Data Domain DD6300 and expansion shelf, in support of DND Workload Migration (WLM) for GPNET. CFSR R3234979 has been opened (2020-12-16).
Backbone Cabling | CM10030589 |  |  |  | DND - New Data Hall (DH) backbone installations at EDC Borden | [5 empty] | Chng Approved | 2020-11-13 |  |  |  | Heidi Mathesius | Heidi.Mathesius@ssc-spc.gc.ca | Oct 01 2020: Change approved at CAB
zLinux (Mainframe) |  |  |  |  | Child RFC GPNET -GPNET MF Migration Activities |  |  | Pre RFC Design Document - LUOps |  | 2020-12-10 | Not Started | 2021-01-13
zLinux (Mainframe) |  |  |  |  | Child RFC GPNET -GPNET MF Migration Activities |  |  | Pre RFC Design Document - LUOps |  | 2020-12-10 | Not Started | 2021-01-13
zLinux (Mainframe) |  |  |  |  | Child RFC GPNET -GPNET MF Migration Activities |  |  | Pre RFC Design Document - LUOps |  | 2020-12-10 | Not Started | 2021-01-13
zLinux (Mainframe) |  |  |  |  | DND Child RFC -TDC MF Migration Activities |  |  | Pre RFC Design Document - LUOps |  | 2021-03-16 | Not Started | 2021-04-07
zLinux (Mainframe) |  |  |  |  | Child RFC TDC MF Migration Activities (eRecruiting)? |  |  | Pre RFC Design Document - LUOps |  | 2021-03-16 | Not Started | 2021-04-07
Active Directory |  |  |  |  | ECD RFC For Build a new phyiscal DC to replace cp0192 ? |  |  |  |  | 2021-02-19 | Not Started | 2021-03-11
[5 empty] | ECD RFC Build a new physical DC to replace cp01191 in TDC? |  |  |  |  | 2021-02-17 | Not Started | 2021-03-09
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: George - Update?
Note on B192: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change cancelled - Gervais to open a new one based on Oct 06 email
Note on F196: Mona Gokani: Discussion on MCSC and RFCs - Meeting Notes Nov 3

## Sheet1
Task Name
WAN Design RFC/Funding/Procurement
SISD Design-oriented RFC - Network WAN
Finalize BoM, Circuit MRC, Facilities Costs for Power and Space
Secure Funding (BOM approved)
Procure equipment
Procure Circuits
Equipment received at Borden
Pre-Implementation work (Test plan, Build Books)
Develop RFCs (infoMan, ECD)
ECD RFC Approved
EDC Borden IT establishment completion
Implementation work (all Sites)
Optical circuits installation/configuration
GCNET-to-GCBB NNI upgrade (adding circuits to GCNET-GCBB (Telcos)
Develop DMP and DRENET migration Strategy
Implementation work (site Specific)
Borden
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration (Upgrade/Config/Cutover/Testing)
LSL II
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration (Upgrade/Config/Cutover/Testing)
400 Cumberland
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration
SHI
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration
PEARKES (DWAN)
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration (Upgrade/Config/Cutover/Testing)
PEARKES (DRENET)
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration (Upgrade/Config/Cutover/Testing)
TUN
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration
HDV
Prep work (DND Child RFC & SSC InfoMan RFC)
Implementation/Migration (Upgrade/Config/Cutover/Testing)
Migrations Completed (WAN Upgraded)
Task Name
TDC CHSS and Misc Security Services
Design
Design Completed
Develop the Design DND Child RFC (SISD)
Develop and Submit DND Child RFC (implementation) pending DND decision on Design RFC
TDC Misc Security Migration Activities
Equipment Arrival
CITS Management
Stage Firewalls for CITS MGMT
Configure firewalls for CITS MGMT
Create MAC Form for CITS MGMT
MAC form approved
Develop and Submit ECD RFC
ECD RFC approved
Ship CITS MGMT to Borden
Facilities to rack/stack and install cables to Switches
Test access to CITS mgmt.
CITS Management RFU
CHSS -Aruba-CP (Chris) - depends on CITS mngt
CHSS
Stage Firewalls for CHSS
Configure firewalls for CHSS
Create MAC Form for CHSS
MAC form approved
Develop and Submit ECD RFC
ECD RFC approved
Ship CHSS TDC F5s to Borden
Facilities to rack/stack and install TDC F5s
TDC/CHSS/SMN switches configure and available
Test
CHSS RFU (VMWARE dependencies)
iAccess (Stephane)
Stage Firewalls for iAccess
Configure firewalls for iAccess
Create MAC Form for iAccess
MAC Form approved
Develop and Submit ECD RFC
ECD RFC approved
Ship iAccess FWs to Borden
Facilities to install/Cable switches
Test access/connectivity iAccess FWs
Cut over interfaces/vlans with test user(s) and all stakeholders [Dependency] for iAccess. Validate service and isolate any issues that come up.
iAccess RFU
Remote Access
Stage Firewalls for Remote Access
Configure firewalls for Remote Access
Create MAC form for Remote Access
MAC Form approved
Develop and submit ECD RFC
ECD RFC approved
Ship Remote Access to Borden/ Facilities to install/cable to switches
Install/Cable switches
Test access/connectivity to Remote Access FWs
Cut over interfaces/vlans with test user(s) and all stakeholders [DEPENDENCY] for Remote Access. Validate service and isolate any issues that come up.
Remote Access RFU
DIG
Stage Firewalls for DIG
Configure firewalls for DIG
Create Mac form for DIG
MAC form approved
Develop and submit ECD RFC
ECD RFC approved
Ship DIG to Borden/ Facilities to install/cable to switches
Test access/connectivity to DIG
Cut over interfaces/vlans with test user(s) and all stakeholders [DEPENDENCY] for DIG. Validate service and isolate any issues that come up.
TDC CITS RFU
Decommissioning of old Firewalls in 101 Goldenrod.
Task Name
DRIMS
TDC Design Completed
TDC Migration Activities
Receive Firewall equipment and SSC Asset Tag
Firewalls received and asset tagged
Pre-configure/stage at 101 Goldenrod
Create Firewall MAC form for Facilities
Submit Firewall MAC form for approval
MAC form approved
Create and Submit ECD RFC for DRMIS Firewalls
ECD RFC approved
Ship DRMIS TDC Firewalls to EDC Borden
DRMIS TDC Equipment Received at EDC Borden
Facilities to install/cable TDC/Inside DRMIS/GPNet switches (Salman TBD)
TDC/DRMIS/SMN switches installed/cabled
DCN to configure TDC/Inside DRMIS/GPNet switches
TDC/DRMIS/SMN switches configured and available
Lift and Shift of physical Server (ITAM/ Chris Warren) and facilities install it
Facilities to install/cable Firewalls (TDC, Inside DRMIS, GPNet)
DRMIS Firewalls installed/cabled
Verify DRMIS firewall connectivity with TDC, Inside DRMIS, GPNet
DRMIS ESXi host made available by DRMIS Team (By DND)
DRMIS ESXi host available
DRMIS to Verify connectivity with ESXi DRMIS server (DND)
Verify DRMIS application access via AnyConnect TDC client (By DND)
DRMIS Relocation and Commissioning Complete
Decommissioning of old DRMIS switches and DRMIS Firewalls in 101 Goldenrod.
TDC PERMIS
TDC Design Completed
TDC Migration Activities
[DEPENDENCY] Receive Firewall equipment and SSC Asset Tag
Firewalls received and asset tagged
Pre-configure/stage at 101 Goldenrod & prepare for shipping
Create Firewall MAC form for Facilities
Submit Firewall MAC form for approval
MAC form approved
Create and Submit ECD RFC for PERMIS Firewalls
ECD RFC approved
Ship PERMIS TDC Firewalls to EDC Borden
PERMIS TDC Equipment Received at EDC Borden
Facilities to install/cable TDC/Inside PERMIS/SMN switches
TDC/PERMIS/SMN switches installed/cabled
DCN to configure TDC/Inside PERMIS/SMN switches (to confirm with Salman)
TDC/PERMIS/SMN switches configured and available
PSS to configure firewalls for SMN TDC (S. Gauthier) to be confirmed with Stephane and Salman
TDC SMN Available
Facilities to install/cable Firewalls (TDC, Inside PERMIS, SMN)
PERMIS Firewalls installed/cabled
Verify PERMIS firewall connectivity with TDC, Inside PERMIS, SMN
PERMIS/DIG ESXi host installed/cabled
PERMIS/DIG ESXi host made available by Windows & Virtualization Team
PERMIS/DIG ESXi host available
Verify connectivity with ESXi PERMIS server by Stephane D.
Verify PERMIS application access via AnyConnect TDC client by DND
PERMIS Relocation and Commissioning Complete
Decommissioning of old PERMIS switches and PERMIS Firewalls in 101 Goldenrod.