## Slide 1: Update on the NextGen Initiative
March 20, 2019

## Slide 2
NextGen Mandate
Budget 2018 announced the government’s intention to identify options for a long-term and sustainable pay system alternative.
OCIO, as the digital advisors, and OCHRO, as the business owner, are working together as the NextGen team to identify options that will be presented in Spring 2019.
NextGen has initiated an iterative dialogue with vendors as a means to identify the technological options that will address the HR and Pay needs of the GC.
A new solution will be driven by the GC’s business needs, which will be informed by engagement with employees, unions, HR practitioners at all stages of design and delivery.

## Slide 3: Applying Lessons Learned to NextGen
2
1. Establishing a Multi-Disciplinary Team
Sense of Urgency
Paying employees accurately and on time is a top priority for any employer and must be treated as a crisis
NextGen is moving at a speed that recognizes the urgency of finding an alternative, sustainable and long-term solution.
Space & Flexibility
A dedicated team/iterative process will enable flexibility to adapt to new evidence and shelter core functions from demands of information
NextGen is working through an agile approach – both in its procurement process and overall approach – in order to course correct as needed.
2. Involving the Right Parties
Holistic Approach
Business needs must drive technology decisions - involvement of HR
NextGen is supported by the CHRO and engages regularly with employees, unions, and HR practitioners at all stages of this process. Engagement will remain an integral part of the way forward.

## Slide 4: Applying Lessons Learned to NextGen
3
Clear Project Lead
Project Lead should be identified to ensure focus and momentum.
NextGen is currently led by the Chief Information Officer of Canada. Governance is achieved through the Deputy Minister Pay Modernizing Committee and Treasury Board Sub-Committee on HR and Pay.
Communication
Project should be open and transparent, with engagement from experts and stakeholders to validate/consult on progress
NextGen has created an open dialogue with public servants, bargaining agents and Canadians through in-person engagements and online platforms.
Project materials have been made public to engage with industry, stakeholders and similar organizations to leverage other lessons learned and best practices to inform this process.
3. Re-build Trust

## Slide 5: Applying Lessons Learned to NextGen
4
Real Life Simulation
Potential solutions must be tested within the GC to ensure systems are able to support a GC environment
NextGen is proposing to carry out pilot(s) with specific departments/agencies to determine possible solutions’ viability in a GC environment.
Change Management
Fully engage departments and agencies and assess change management across the GC.
NextGen will evaluate change management requirements– e.g. workforce consideration, current capacity of compensation advisors, level of training required, as well as a plan that encompasses data integrity and quality.
Pilot departments/agencies will be equipped with the necessary resources and funding in order to be successfully involved in the process.
4. Robust testing and change management before Implementation

## Slide 6: Public Environment – Union Engagement & Reactions
Regular Briefings
Monthly basis – Joint Union Management Committee
Provide updates on progress, seek input into gate requirements, evaluations, and user testing.
Union Response
Positive – both online and in-person
Supportive of approach that seeks union input
Inclusive – supportive of member engagement through User Expos

## Slide 7: Public Environment
Testing with users (260+ public servants)
Testing with subject matter experts (60+)
As a result of these evaluations in Gate 2, three vendors were successful in advancing to Gate 3 of the procurement, which is currently underway.
Evaluations
User Expos
External Communications
Informal testing with public servants (2000+) as part of a series of User Expos held between January 14 and February 14, 2019
Provided good opportunities to engage with media
Enhanced an open dialogue on social media platforms
The User Expos were held in Ottawa, Gatineau, Montreal, Dartmouth, Victoria, Edmonton, and Winnipeg to obtain feedback on possible solutions, with respect to the user interface. The response to date has been positive.
A Digital User Expo will be launched in April to recreate User Expos in a web based format to allow for broader engagement.
Proactive, multi-platform approach
Feature opportunities for ministers to show progress
Post-budget communications are planned and will note the progress to Gate 3 in the procurement process and echo any potential Budget commitments
Regular and proactive communications will continue into leading up to a spring ministerial announcement around options.

## Slide 8: Progress on Procurement
Gate 3
Will launch in
March 2019
Gate 2
Launched in November 2018
Gate 1
Launched in October 2018
Vendors demonstrated how their solutions aligned with GC Digital Standards through bid documentation.
Potential solutions were evaluated against GC business capabilities, outcomes and solution architecture; hands on user experience; and, the implementation, support, accessibility and partnership experience.
Gate 3 will close before end of spring.
Three vendors have advanced to Gate 3 and will be required to co-design deployment models, provide advice on data cleansing and migration, determine implementation, maintenance and on-going costing, and demonstrate change management capacity, and provide contract terms and conditions and service level agreements.

## Slide 9: Risks and Risk Mitigations
GC proposes running a pilot to test solutions with GC pilot departments/agencies. NextGen is currently working on the scope of pilots and criteria to identify potential pilot departments/agencies
Vendor solutions do not support a GC environment
Risk
Open/transparent communications strategy, innovative agile process to restore trust and develop awareness on the initiative as it proceeds.
GC credibility is challenged, lack of trust in implementation/success
Risk
Agile process will pre-qualify up to three possible vendors to partner with the GC, with one successful vendor HR/pay pilot. In the event of failure, pre-qualified vendors can be piloted in lieu of starting over.
Pilot fails
Risk

## Slide 10: Risks and Risk Mitigations
Continued commitment to transparency will ensure that a realistic depiction of progress is shared to not heighten public expectations for success.
Expectations on potential success may be overly optimistic
Risk
A fairness monitor has been engaged throughout this process, as well as third-party private sector advice. The initiative has adopted an open and transparent process on design, criteria and project documentation.
Vendor complaints on the agile process resulting in a lack of will to pursue pilots
Risk

## Slide 11: Milestones and Next Steps
AUGUST - SEPTEMBER
OCTOBER
NOVEMBER
DECEMBER – FEBRUARY
Launch of Phase 1 of the Agile Procurement
Initial User Engagement through HR Workshops
Vendor Industry Day
Launch of Gate 1 of the Agile Procurement
Government User Day
Online Engagement (LeadersGC)
Sentiment Analysis Launched
User Expos
Launch of Gate 2 of the Agile Procurement
Architecture Day
PROGRESS TO DATE
Ongoing work on options analysis, change management and scope of business transformation to inform the development of a Treasury Board submission.

## Slide 12: Milestones and Next Steps
MARCH - APRIL
MAY
JUNE – JANUARY 2020
JANUARY 2020 – JANUARY 2021
Launch of Gate 3 of the Agile Procurement
Launch of the Digital User Expos
Executive Day
Budget 2019
Recommended Options
Completion of potential pilots (*pending source of funds)
Preparation for potential pilots (*pending source of funds)
NEXT STEPS