## Introduction
An organization undergoing change must evaluate its readiness. The Project Readiness Assessment provides an organization with a framework to determine if the key enabling elements are in place for their organization to have a successful workplace change. These enablers are critical factors that support the success of a modernized workplace. The modernized workplace does not solely transform the physical office space; it is an integrated workplace solution that drives virtual and behavioral changes leading to business transformations and a cultural shift in line with Destination 2020 and its vision for the public service of the Government of Canada. This assessment will be used to identify readiness but also potential challenges, gaps, and opportunities that should be addressed before, or as part of, the project implementation plan. The assessment will ensure that organizations are in line with the onboarding criteria of any workplace modernization project:
ü Demonstrate leadership (senior executive level) towards Destination 2020 principles, supporting a knowledge-based, mobile, collaborative, and innovative workforce
ü Commitment to supporting the unassigned workplace, where principally all employees will be empowered in an environment of trust, to select their workpoints based on their activity requirements and personal preferences. This may include access to telework.
ü Demonstrate readiness, or a roadmap, towards IM/IT transformation in the virtual environment in support of mobility and collaboration
ü Commitment to managing change through communications and engagement with employees
ü Support participation in the ABW program’s performance measurement process, consisting of pre- and post-occupancy surveys to provide design and organization feedback and lessons learned to ensure successful implementation.
Instructions:
1. This Self-Assessment can be completed individually or as a group with the project team members, champions and senior managers involved in the project.
2. For each question enter the number that best represents your organization
3. You can provide additional comments for each theme if required
4. The results from this assessment are gathered on the Results and Guidance tab of this document
5. The results are subjective, there are no right or wrong answers

## Self Assessement
PROJECT INFORMATION (greyed out areas to be completed by PSPC) | [5 empty] | ORGANIZATION
[6 empty] | The organization is agile and able to adapt and change to meet new challenges. | Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1
Department: | [5 empty] | Our organization identifies and prioritizes its’ desired results | 3
Proposed Location and area (m2) - if known | [5 empty] | Performance indicators are developed to measure the progress and level of success of changes | 3
Participating FTEs (approx. #) | [5 empty] | Employees view change as an opportunity | 3
Project Cost (est.) | [5 empty] | Major change initiatives were successfully implemented in the last 2 years. Please provide a list in the comments if possible. | 3
Project Timeline: | [5 empty] | Our organization is open to new ideas and innovation | 3
Additional Comments if required | [5 empty] | Our organization is committed to its internal Destination 2020 objectives promoting innovation, collaboration, knowledge-based workforce and employee health and wellness | 3
[6 empty] | This is the right time to implement workplace transformation (i.e., it will not compete with other major changes currently being made)? | 3
Additional Comments if required
BUSINESS PROCESSES | [5 empty] | SPACE
| Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1 | The workplace supports the organization activities and the accomplishment and | Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1
Our organization’s common business processes are automated (no paper required) | 5 |  |  |  |  | Some of the office space within our organization is unassigned | 5
Our organization uses e-signatures for common internal administrative approvals | 4 |  |  |  |  | Meetings rooms are centrally managed and available to all employees (i.e. through a reservation system) | 5
Some employees in our organization are certified or trained to improve processes and engage the right people/stakeholders (e.g. LEAN) | 3 |  |  |  |  | Our office space currently offer shared collaboration areas (non-bookable) | 5
Additional Comments if required | [5 empty] | Additional Comments if required
RESOURCES / PROJECT | [5 empty] | PEOPLE
Involving the right people in a workplace renewal project at every step of the project is key for success. | Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1 | Providing the space, the tools and the framework to our employees to perform their functions. | Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1
Resource(s) to manage the project are available | 4 |  |  |  |  | Managers manage by results and not by presence | 3
Resources to implement key enabling elements are available ( where required in IM, IT, HR, process transformation) | 3 |  |  |  |  | Employees work outside of their assigned workstations or offices | 3
Resource(s) to manage the integration of all the key enablers is available | 1 |  |  |  |  | Telework is supported with policies, agreements and/or other mechanisms supporting telework available to employees | 2
Resource(s) for change management are available | 1 |  |  |  |  | The culture of our organization is supportive of working in a mobile/flexible way | 3
Resource(s) to provide training to employees are available | 1 |  |  |  |  | The culture emphasizes the importance of teamwork, information sharing and collaboration | 2
Resource(s) to provide communication advice and develop communications products is available | 2 |  |  |  |  | Employees are knowledge workers empowered to make choices about when, where and how they work based on what makes sense | 2
Additional Comments if required | [5 empty] | Additional Comments if required
TECHNOLOGY | [5 empty] | LEADERSHIP
Technology is a key enabler to change the workplace and people’s work mobility. | Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1 | Ensuring there is active and engaged sponsorship for the change at a senior executive level within the organization to achieve the desired results. | Strongly Agree 5 | 4 | 3 | 2 | Strongly Disagree 1
Employees are equipped with a Laptop and or a Notebook, and if not, an IT roadmap is underway (implementation within next 2 years) to replace current IT equipment with mobile devices, where required | 3 |  |  |  |  | Our organization has a clearly defined workplace vision and strategy | 2
Employees are equipped with mobile telephony, and if not, a plan is underway to replace fixed telephony with mobile telephony (implementation in the next 2 years) | 3 |  |  |  |  | The vision and strategy of the project is being supported by a project Champion (person who is an advocate for the project and is focused on the benefits to the organization) | 3
Wi-Fi is currently in use across the department | 1 |  |  |  |  | The workplace transformation objectives are aligned with the strategic priorities of the organization. | 3
Our organization has implemented a central electronic record information management system (e.g. GCDocs)? | 3 |  |  |  |  | Workplace transformation has an executive sponsor (person who is the project owner - authorize, fund and have authority over the delivery) | 3
Our electronic record and information management system contains the majority of our active information assets and is being used by most of our employees | 4 |  |  |  |  | The executive sponsor has the necessary authority over the people, processes and systems to authorize and fund the necessary changes (i.e. key enablers). | 4
Our organization has videoconferencing facilities available for all employees | 3 |  |  |  |  | The executive sponsor is able to build a sponsorship coalition for the change | 4
If applicable, our organization has implemented a secure network and all employees who require it for their work have access to it | 3 |  |  |  |  | The executive sponsor will participate with the project team throughout the entire project | 4
Meeting rooms are equipped with easy to use technology that supports presentations, collaboration and information sharing | 3 |  |  |  |  | Additional Comments if required
Additional Comments if required
To see the results of this self-assessment questionnaire, please go to the next tab - Results and Guidance
Note on H4: Michael DeKelver: This is normal for all department authorities, thus all will agree! Do we want to say that the department identifies importance to workplace, its support for employees and the leadership and championing of workplace and the integrated project team?
Note on H7: Michael DeKelver: Could we strenghtn with a change sponsorship assessment question Example: Leadership exists to champion change and communications to support employees through this transformation; *The department has an established change management function, and/or demonstrates support and establishes capacity to manage transformation and the employee change
Note on H9: Michael DeKelver: Suggest: Beyond 2020 objectives of Agility, Inclusion and Equipped; and is open to extending these dimensions to the workplace
Note on H18: Julie Jocelyn: Something is missing here...
Note on H19: Julie Jocelyn: Suggest adding at the end (enclosed offices and/or open workstations)
Note on H39: Michael DeKelver: Or has sufficient leadership commitment to create one when required?
Note on H41: Michael DeKelver: This is a great piece to strengthen in the workplace strategy framework, part of the organizational scan and <Strategize> process

## Results and Guidance
How to read the results of your self-assessement? ❶ Your self-assessment results are identified on the right hand side with colour coded icons which will provide you with a subjective readiness level for each of the categories. You can refer to the guidance and advice area below, to help you with the planning of your workplace transformation project. ❷ A visual graphic is also provided to you, to give you a better visual of your readiness against the target. |  |  | Organization | People | Business Processes | Technology | Space | Leadership | Resources
| Self-assessment score |  | 3 | 2.5 | 4 | 2.875 | 5 | 3.2857 | 2
| Optimal Target |  | 5 | 5 | 5 | 5 | 5 | 5 | 5
Categories indicating a green light should be leveraged and maintained. Categories indicating a yellow or red light highlight areas where the organization is not fully prepared or at risk and should focus on actions that would bring the organization to the next level. Representatives from PSPC working with you to modernize your workplace can provide you with guidance to ensure your success (i.e. Project Director, Project Leader, Design Manager, CM Manager, ABW Program Manager, etc.).
| Organization | 70 | Your organization show signs of maturity and has an established business plan and knows how to deliver it. Innovation and openness to change are promoted and your organization has a clear vision and defined objectives of what they wish to achieve by transforming their organization. Performance measurement indicators are commonly used tools as well as objectives, benefits and vision and they can easily be brought to bear on a workplace transformation initiative.
|  | 55 | It is important that the objectives, performance indicators and potential benefits that can be attained from adopting an activity based workplace are integrated into and overall vision for the organization. Including that they be identified, documented, baselined, measured and reported to ensure that the return on investment is maximised. It is recommended that a document be developed which outlines the overall approach.
|  | 30 | To onboard a project, an organization must articulate a vision and set objectives to transform the way they are working. A modernized workplace is one of the key enabling elements that will support the transition towards an innovative, collaborative and knowledge-based organization. Organizations should begin to think about their vision for the future, and include the people/culture, space and technology perspecpectives, and from there, determine how and when modernization fits in.
| People | 70 | Your organization knows how to manage and support changes; employees demonstrate an ability to deal positively with changes as opposed to ignoring or resisting them. The workforce is agile, delivers by results and a relation of trust has been established. A modernized workplace provides you with a design that builds on these attributes.
|  | 50 | A modernized workplace is not just about the space. It is a significant cultural and organizational change as well as providing the right tools, the variety of space and the framework to your employees to empower them to deliver their functions. Changes to culture, policies and directives such as performance management by result, telework, etc. allows greater flexibility and empowerment for your knowledge based workforce. Leadership based on trust and performance results is key.
|  | 30 | An assessment of the culture of the organization with respect to the adoption of a new workplace can provide an important insight into the effort required in terms of stakeholder engagement and communications to move forward successfully. A modernized workplace requires different working practices which means that policies and guidelines should be reviewed to accommodate the new way of working (performance management by results, mobility, flexibility, teleworking, security, etc.).
| Business Processes | 70 | Your business processes are mostly automated and not paper based. For an even stronger alignment to a modernized workplace model, ensure that all your current business processes will meet the need of a mobile workplace. It's important to review processes in collaboration with users on a regular basis to assess and refine as required.
|  | 55 | You need to examine what business you are in, what processes support what you do, and determine how the new workspace and technologies will impact your processes. In collaboration with the subject matter experts and business processes owner, list all business procedures that might be impacted by moving to a modernized workplace and identify processes that might have to be addressed (e.g. e-signature, documents approval, correspondence, workflow, finance and HR processes, etc.) If you need to reduce paper file storage, it is a good idea to organize an information paper clean-up campaign.
|  | 1 | If most of your business processes are not automated, it is recommended to start investing in a comprehensive business process review. There are a number of techniques (BPM, Lean, SIGMA) and training available to analyze and review your current processes Once the existing processes have been captured, then a new automated and paper free process can be defined, so that employees can understand how the workflow will change as a result of the introduction of new technology. It is almost impossible to work in a mobile way if you are weighed down with paper based processes.
| Technology | 78 | Your organization already has or is implementing an IMIT Strategy and Roadmap to move from desktop computers to laptops/notebooks, smartphone, IT enabling equipment with the infrastructure to support them and to support electronic record management. This is a major consideration for moving to a modernized environment which is based on mobility and a work-anywhere-anytime culture.
|  | 50 | Your Information Technology group may already have a strategy in place to implement mobile technology. Implementing a modern workplace relies on the right technology to be in place to support mobility. The following elements must be in place: Laptop computers or Tablets, Smart/Cell phones, MFD Printers, videoconferencing equipment, IT equipment to enable sharing of information and collaboration, Electronic Information Management System. Piloting of the chosen technology before wide scale roll-out is recommended as it allows staff to try the new hardware in actual case settings. An appropriate evaluation of the pilot, can identify whether the hardware is ‘fit for purpose’ or whether other hardware options should be considered further.
|  | 30 | To implement a modern workplace, the right technology must be in place to support mobility. The development of an IMIT strategy and roadmap must be developed including moving from: ▪ Desktop computers to laptops/notebook ▪ Landline phone to cell/smart phone ▪ Paper document filing and storage to electronic records management system ▪ Personal and decentralize printer/scanner to Multifunctional print anywhere devices ▪ Traditional boardroom to smart meeting room ▪ And systematically address the processes as systems within your organization that create paper.
| Space | 89 | Your initiation of a re-fit of your workspace means you've identified an opportunity to transform your workplace to be innovative, collaborative and to support greater workforce mobility. When planning and designing ABW keep in mind that there is no one size fits all. There are a wide variety of models allowing you to explore what best suits your business and objectives. Space as a component of workplace becomes a strategic partner driving towards your business outcomes. You've already taken important steps towards this by centralising the management of spaces. User friendly desks and office booking systems are also available and could be part of your project plan.
|  | 50 | Consideration should be given to scalability and the degree of flexibility desired in your project. Because a modernized workplace relies on accommodation management taking on a more active and strategic role in how space supports broader business outcomes , it's important to begin to take steps now to break space entitlement and support the sharing of space.
|  | 30 | Introducing an activity based workplace to a more traditional organization will require a lot of engagement and some time to do it effectively. It would be worthwhile to develop a small pathfinder to demonstrate to employees and management the benefits and the functionality of a flexible shared workplace. The pathfinder area could host monthly residents and would act as a great change management tool. Guided tours and opportunities for open discussions could also be organized.
| Leadership | 75 | The executive leader is on board with your workplace transformation project and is ready to support, participate, build coalition and communicate. Your leaderundertands the reasons for the change, will articulate them and will become a visible early advocate of ABW and will drive your organization to reach its goals and achieve its vision. Make sure to create these opportunities.
|  | 50 | An active and visible executive leader is the number one contributor to successful change and applies to a workplace transformation project. This leader must participate actively and visibly throughout the project, build coalitions and communicate directly with employees about why the workplace change is needed. Ensure senior management is fully on board with this project as moving to a modernized workplace will require strong support and advocacy from the C-suite.
|  | 25 | Establishing the vision by clearly defining and communicating what is to be achieved is key into implementing a modernized workplace. Senior Management must be engaged in this visioning to set the scope and approach of the transformation initiative, from there identifying the right executive leader and senior managers responsible for key decisions, to engage counterparts and build coalitions, and communicate the vision. These are necessary steps before onboarding an ABW project.
| Resources | 75 | An efficient governance structure is in place to ensure delivery of your project and change management has been integrated along with project management from the planning phase of the project. Key enabling resources are allocated (financial, human, security, IT, communication, OSH, etc.) for the success of this business transformation project. Noting lessons learned and celebrating success are equally important activities along the way, and after moving in, to ensure that new workplace is well adopted.
|  | 50 | A governance structure should be established at the organizational level, and should include the executive leader, executive sponsor, project leads, change manager, and the various key enabler leads for the workplace transformation project (financial, human, security, IT, communication, OHS, etc.). Change Management addresses the people side changes associated with the new workplace; a commitment to follow an established change management strategy is very important.
|  | 25 | Before establishing a governance and project structure, the executive sponsor who has the necessary authority over the people, processes, funds and system should be identified and set the governance that should be put in place (see above). A workplace modernization project requires significant change management support at all stages of the journey. You can have the latest and greatest technology and beautifully designed workspace, but if your employees have not bought in to why the organization is changing, and if they can't see the benefits of a modernized workplace, they will not make the necessary changes to their behaviours and practices and the intiative will fail.
What is Activity BASED WORKING (ABW)?
Philosophy
To make work more effective and efficient but also more enjoyable for both the organization and the employee. This is realized by focusing on the employees and giving them the freedom (within boundaries) to decide for themselves how to work, where to work, when to work, the tools to use and with whom to collaborate to get the work done.
Concept
ABW is a concept which recognizes that through the course of any day, people engage in many different activities and that they need different types of work settings to accommodate these activities.
* Definition and concept from Veldhoen+ Company
ON BOARDING CHANGE READINESS CRITERIA
▪ Demonstrate leadership (senior executive level) towards Destination 2020 principles, supporting a knowledge-based, mobile, collaborative, and innovative workforce
▪ Commitment to supporting the unassigned workplace, where principally all employees will be empowered in an environment of trust, to select their workpoints based on their activity requirements and personal preferences. This may include access to telework.
▪ Demonstrate readiness, or a roadmap, towards IM/IT transformation in the virtual environment in support of mobility
▪ Commitment to managing change through communications and engagement with employees
▪ Support participation in the program’s performance measurement process, consisting of pre- and post-occupancy surveys to provide design and organization feedback and lessons learned to ensure successful implementation.
Employees BENEFITS OF A
MODERNIZED WORKPLACE
▪ increased engagement
▪ increased communication and collaboration
▪ increased flexibility, productivity and innovation
▪ employees feel empowered
▪ builds a relationship of trust
▪ support wellbeing and health at work
▪ employees have choice from a variety of workpoints
▪ to meet their social, information, and behavioural needs
Organizational BENEFITS OF A
MODERNIZED WORKPLACE
▪ creates an inspiring workplace
▪ attracts and retain top talent
▪ increases space utilisation, sustainability and flexibility
▪ achieve your departmental Destination 2020 objectives
▪ a mobile, collaborative, flexible workplace
▪ accommodates future organizational growth
▪ accommodates diversity of personal and professional preferences
INTEGRATION
Ensure there is equal focus on the people, technology and space elements of the change. There is no point providing people with a suite of great collaboration and concentration spaces if they don't have mobility enabling technology to go and use them and their leader still equates "work" with sitting at a desk.
A MODERN GC WORKPLACE
Flexible
Efficient
Healthy
Collaborative
Digital
Inclusive
Green
Note on E17: Julie Jocelyn: Suggest removing ABW and using a GCworkplace.