## What is the CM Workbook
CM Workbook
Completing the PRET form is a prerequisite before using this workbook.
Attend the CM Kick-Off Session to understand how to use this workbook.
This workbook is the first tool to explore when opening this program. It includes several documents that you will be able to use a reference throughout the project or to use on a more recurring basis. This workbook will assist you in identifying key elements or organizational attributes that are specific to your organization and that will allow you to adapt the proposed generic change management strategy and personalize it for your organization. More information is provided in the CM workbook directly or you can communicate with us to organize a CM Kick-Off Session.
This CM Workbook includes several documents to:
Analyze the impact of the changes on employees
Validate the stakeholders and contributors of the project
Identify certain risks, challenges and opportunities
Plan the implementation and sequence of change management activities
Measure the effectiveness of program activities
The proposed sequence to use the various tools in the Workbook is as follows:

## PRET
Project Realization Evaluation Tool (PRET)
organization:
project location:
Key Project Resources
|  |  | Capacity to support the project | Level of influence | Level of interest | Support for the project
Project manager/accomodations lead
Name
Title
email contact
Project sponsor
Name
Title
email contact
Executive sponsor
Name
Title
email contact
Change manager
Name
Title
email contact
Communications representative
Name
Title
email contact
Facilities/Design representative
Name
Title
email contact
IM representative
Name
Title
email contact
IT representative
Name
Title
email contact
HR representative
Name
Title
email contact
Security representative
Name
Title
email contact
OHS representative
Name
Title
email contact
Indigenous Employee Group
Main contact Name
Title
email contact
Diversity, Equity, and Inclusion Employee Group(s)
Main contact Name
Title
email contact
Organizational and Project Vision
What is your organizational wide vision for future of work and/or workplace modernization? Insert below.
What is your organization's Vision for a Workplace Transformation project? Insert below
What is your organization's Hybrid work model? Insert below
Project Management Readiness Assessment
Sponsorship
Our organization's workplace strategy is being supported by a project sponsor that can be active and visible throughout the entire project. The project sponsor has the necessary authority over the people, processes, and systems to authorize and fund the necessary changes.
Leadership
Our organization's senior leaders have made workplace modernization a priority. Senior leaders are ready to communicate this change in the context of other competing priorities and are willing to walk the talk.
Key enablers
Our organization has developed a workplace modernization strategy and has the necessary resources to implement the strategy, including project champions, a project integrator and subject matter experts.
Change management, communications and training
Our organization has a structured change management approach for the project and has identified trained resources for change management. Resources are available to provide communication advice, develop communications products and provide training to employees.
Change Readiness Assessment
History of change
Our organization's history of change is successful, employees have embraced the past changes and did not revert back to old ways.
Culture of Innovation
Our organization is open to new ideas and innovation, employees are rewarded for risk taking and embracing change.
Leadership and Managers
Senior leaders and managers in our organization are highly skilled at managing change, performance is evaluated based on results and not based on employees’ presence.
Hybrid Work
Employees in our organization are encouraged, trusted and empowered to make choices about when, where and how they work based on what makes sense. Remote work (i.e. telework) is supported with policies, agreements and/or other mechanisms.
Client Enabling Initiatives
Enabling Sector |  | Client Enabling Initiatives |  |  |  | Status
Information technology (IT) |  | Secret/classified network access
Information technology (IT) |  | Print-on-demand
Information technology (IT) |  | Audio-visual equipment (videoconferencing , Clickshare, etc.)
Information technology (IT) |  | Collaboration tools and platforms (MS Teams, Miro, Slack, etc.)
Information technology (IT) |  | Applications via phones (elevator, access card, booking system, etc.)
Information technology (IT) |  | Booking system
Information technology (IT) |  | Cloud-based tools and software (Microsoft 365, OneDrive, etc.)
Information technology (IT) |  | Wi-Fi: private and/or public
Human resources (HR) |  | Policies and directives adapted to hybrid working
Human resources (HR) |  | Community norms / team charters
Human resources (HR) |  | OHS: Assignment of first aiders
Human resources (HR) |  | Interim work agreement / telework agreement
Human resources (HR) |  | Managing employees in a hybrid working model
Human resources (HR) |  | Onboarding of new employees in a hybrid working environment
Information management (IM) |  | Digitization (paper storage space reduction)
Information management (IM) |  | Imaging services
Information management (IM) |  | Implementation of an information management system (GCdocs, SharePoint, EDRMS, OneDrive, etc)
Information management (IM) |  | Digitalization of processes
Security |  | Emergency procedures
Security |  | Access card system
Security |  | Working with protected/confidential information in a shared space
Security |  | Assignment of Fire Warden role
Facilities and interior design |  | Access to and working in an ecosystem of spaces
Facilities and interior design |  | Activity-based working environment: shared seating
Facilities and interior design |  | Activity-based working environment: workpoint variety
Facilities and interior design |  | Activity-based working environment: work zones
Facilities and interior design |  | Ergonomics, accessibility and inclusivity in all workpoints
Facilities and interior design |  | Smart office (lights, temperature regulation, auto blinds, etc.)
Facilities and interior design |  | Utilization of day lockers
This form is for you! It should be filled out as best as possible by the project lead and help from the intergrated project team. The PSPC SWAG team will review and help fill in the gaps when necessary. This is an evergreen document and should get updated throughout the project.
Purpose: to provide your change manager with the necessary information to identify the gaps, and determine where the change management activities should be focused.
For each statement below, select a statement in each drop down menu that best represents your organization.
Workplace modernization is more than just a space upgrade. It involves many other internal initiatives to ensure the modernized space can work effectively. Below is a list of common internal initiatives. Select a status for each one to determine the level of effort required from each enabline sector for your project.
Tip: Your project vision should be clear and to the point. It should be easy for employees to understand and get onboard. Your project vision should define the desired outcomes of the project at a high level (ie: Offers modern, open, airy, and bright spaces that inspire people, and/or Supports employees’ health and well-being), and provide details on the scope of the project (ie: address of the modernized space, branches and/or sectors affected, how the space is intended to be used, who will have access to the space). The vision should also link back to your organizational vision as well as the GCwide vision.
Tip: Your vision for your hybrid work model should be clear and to the point. It should be easy for employees to understand what is expected of them and how they will work going forward. If your organization is choosing to experiment with different models, make sure to reinforce that message with statements such as ''with flexibility in mind, this working model may evolve over time based on employee feedback''. If you are taking a more prescribed approach, make sure logistics on how the days in the office work.

## Change inventory and impacts
Change Inventory and Impact Assessment
Enabling Sector | Client Enabling Initiatives | Status | Change Impact
Information technology (IT) | Secret/classified network access | 0 | Low
Information technology (IT) | Print-on-demand | 0 | Low
Information technology (IT) | Audio-visual equipment (videoconferencing , Clickshare, etc.) | 0 | Medium
Information technology (IT) | Collaboration tools and platforms (MS Teams, Miro, Slack, etc.) | 0 | Medium
Information technology (IT) | Applications via phones (elevator, access card, booking system, etc.) | 0 | Medium
Information technology (IT) | Booking system | 0 | Medium
Information technology (IT) | Cloud-based tools and software (Microsoft 365, OneDrive, etc.) | 0 | Medium
Information technology (IT) | Wi-Fi: private and/or public | 0 | Low
Human resources (HR) | Policies and directives adapted to hybrid working | 0 | High
Human resources (HR) | Community norms / team charters | 0 | Medium
Human resources (HR) | OHS: Assignment of first aiders | 0 | Low
Human resources (HR) | Interim work agreement / telework agreement | 0 | High
Human resources (HR) | Managing employees in a hybrid working model | 0 | High
Human resources (HR) | Onboarding of new employees in a hybrid working environment | 0 | Low
Information management (IM) | Digitization (paper storage space reduction) | 0 | Medium
Information management (IM) | Imaging services | 0 | Low
Information management (IM) | Implementation of an information management system (GCdocs, SharePoint, EDRMS, OneDrive, etc) | 0 | High
Information management (IM) | Digitalization of processes | 0 | Medium
Security | Emergency procedures | 0 | Low
Security | Access card system | 0 | Low
Security | Working with protected/confidential information in a shared space | 0 | Low
Security | Assignment of Fire Warden role | 0 | Medium
Facilities and interior design | Access to and working in an ecosystem of spaces | 0 | Medium
Facilities and interior design | Activity-based working environment: shared seating | 0 | High
Facilities and interior design | Activity-based working environment: workpoint variety | 0 | Medium
Facilities and interior design | Activity-based working environment: work zones | 0 | Medium
Facilities and interior design | Ergonomics, accessibility and inclusivity in all workpoints | 0 | Low
Facilities and interior design | Smart office (lights, temperature regulation, auto blinds, etc.) | 0 | Low
Facilities and interior design | Utilization of day lockers | 0 | Medium
Use the information collected on the PRET tab to validate the change impacts (column H) for each of the initiatives. We've pre-populated the Change Impact column based on the scope and context of most projects in the Workplace Transformation Program, however, conditions specific to your project or organization could raise or lower the impact for each one. Consider the following when determining impact: level of effort required to manage each initiative, level of risk associated to the initiative, number of impacted employees, timing, as well as factors identified on the PRET tab for the team/representative leading each initiative (ie. level of interest, of influence, etc.)
Purpose: To help determine priorities and identify gaps that need to be addressed in your CM Strategy.
Note: The CM Strategy proposed in the CM Program in-a-box addresses conditions based on the change impacts as they are presented here. If you modify the impacts and raise them (low to medium, low to high or medium to high), consider how this may affect your CM Strategy.

## Contributors Table
Contributors Table
Contributor group | #FTEs (full-time employees) | Type of contributor | Level of influence | Level of interest | Support for the project | Opportunities | Challenges/Barriers | First/Next action
Senior Leaders (DM, ADM, DG and Directors) |  | Sponsors (S) | High | High | Neutral |  |  | Use the 'Communication Template to announce project to leadership team'
People Managers |  | Sponsors (S) | Medium | High | Neutral |  |  | Use the 'Communication Template to announce project to leadership team'
Branch 1 Employees |  | Impacted (I) | Low | High | Neutral |  |  | Use the 'Communication Template to announce project to employees' once it's been announced to Senior Leaders and People Managers
Branch 2 Employees |  | Impacted (I) | Low | High | Neutral |  |  | Use the 'Communication Template to announce project to employees' once it's been announced to Senior Leaders and People Managers
Branch 3 Employees |  | Impacted (I) | Low | High | Neutral |  |  | Use the 'Communication Template to announce project to employees' once it's been announced to Senior Leaders and People Managers
Offsite People Managers (of Impacted Employees) |  | Indirectly Impacted (II) | Medium | Medium | Neutral |  |  | Use the 'Communication Template to announce project to leadership team'
Union(s) |  | Indirectly Impacted (II) | High | High | Neutral |  |  | Present your WTP project to your union(s) as early as possible in the process and Keep them informed with regular updates.
Canadians |  | Indirectly Impacted (II) | Low | Low | Neutral |  |  | Keep this contributor informed, specifically on the direct impacts to them, ie. If your address is changing, processes being updated, etc. [content not included in the box as this is specific to each organization]
External Contributors / ‘Clients’ |  | Indirectly Impacted (II) | Low | Low | Neutral |  |  | Keep this contributor informed, specifically on the direct impacts to them, ie. If your address is changing, processes being updated, etc. [content not included in the box as this is specific to each organization]
Use this table to identify the various impacted groups. Depending on the scope of your project, consider if you will group all employees together (best approach for projects that impact only a portion of the organization or projects that are only 1 floor) or separate them as proposed in the table below (best approach for fully impacted organizations or full building fit-up). We've pre-populated some columns based on the scope and context of most projects in the Workplace Transformation Program, however, condition specific to your project or organization could change some of the answers. Column G, H and I can be filled during the CM Kick-Off Session with the help of the PSPC Change Experts. Depending on the information that changes in the various columns, the First/Next action may need to be revised.
Purpose: To identify potential opportunities or challenges for specific groups and address them in your CM Strategy. To identify your First/Next action for each group to include that information in your PM-CM Integrated Plan (next tab).
Note: If your Next/First action activities are not covered via one of the activities proposed in the CM Program in-a-box, they will need to be added to the PM-CM Integrated Plan.

## PM-CM Integrated Plan How-to
IMPORTANT INFORMATION ABOUT THE PM-CM INTEGRATED PLAN–MUST READ BEFORE BEGINNING
The calendar portion located on the right of the “CM-PM integrated plan” worksheet is auto-filled based on the information entered in the “Status”, “Start date” and “End date” columns, and on the formula of the “Days” column.
The worksheet provides a visual representation of the schedule; however, there is no link between activities or delays as there would be in Microsoft Project.
1. This worksheet has elements that should not be deleted; otherwise, the functionality will be compromised. The following elements should not be removed or modified:
- Rows 1-8, except for the text in red and the titles for row 7 columns.
- Note: row 8 is hidden and contains the formula that highlights the current day in the schedule; do not remove!
- Columns “Status”, “Start date”, “End date” and “Days”
- ALL columns to the right of the “Days” column, except for the legend at the very top, if you need to modify it.
- The scroll bar at the top of the schedule
2. Project start date: Before using the schedule, you must specify the start date in cell I5. If you wish to hide this information for printing purposes, you can change the colour of the cells (F5 to I5) and font to white.
3. Scrolling increment: Changing the number in cell I6 will make you move forward in the schedule. 1 increment = 1 day. You can also use the scroll bar in the schedule to do the same. If you wish to hide this information for printing purposes, you can change the colour of the cells (F6 to I6) and font to white.
4. Scroll bar: It is located at the top of the schedule just below the dates; it is light grey with a darker grey square. You can drag the grey square to move forward or backward in time (up to the Project start date) or click on the bar on either side of the sqaure to move on the timeline. To quickly return to the project start, you can type 0 in cell I6.
5. Adding/removing rows:
- Row 11 is an example and should be removed. You can also delete any of the activity rows that do not apply to your project.
- Always ensure to add rows below row 11 (first row) or above row 110 (last row) to ensure they are captured in the formulas.
- Once you’ve inserted new rows, you will need to copy the formatting into those new rows by copy/pasting an entire existing row. You can use any activity row for this or one of the blank ones located at the bottom.
6. Adding/removing columns:
- Adding additional columns can be done as long as it is to the left of the “Days” column.
- You can remove any column with the exception of the “Status”, “Start date”, “End date” and “Days” columns.
7. Columns:
- Project phase: Use the pull down list to select.
- Type of activity: Use the pull down list to select.
- Activity: The activities listed here are the activities listed in the CM Program in-a-box and may not apply to your specific project.
- Lead: Write the name of the person or group leading the activity.
- Notes: Enter any additional information required for the activity.
- Status: Use the pull down list to select. The status selected changes the colour of the cells in the calendar portion on the right (once the "Start date" and "End date" columns are filled). The status does not impact the "Progress" column.
- Progress: Enter any value between 0 and 100. Incremental grey shading will be automatically applied in that cell. The information in this column is not linked to any other column. For example, marking an activity as “Complete” in the “Status” column will not mark the “Progress” cell as 100%; it needs to be done manually.
- Start date: Enter start date in the format shown. Date must be after the “Project start date”.
- End date: Enter end date in the format shown. Date must be at least 1 day after the “Start date”, and must be after the “Project start date”.
- Actual end date: Enter actual end date in the format shown. The information in this column has no impact on the calendar portion of the worksheet.
- Days: Automatically generated from the information in “Start date” and ‘”End date” columns. Do not enter manual numbers.
8. Text in red in the worksheet needs to be modified:
- Row 3: Client name, Project name, Address
- Row 4: Created by
- Row 5: Project start date (see item 2 above)
- Row 8: Date
HOW TO USE THIS WORKSHEET
The rows are presented in the sequential order of activities presented in the CM Program in-a-box, with the PM Program activites listed below in no particular order.
- Once you’ve set up the worksheet as described above, you should start by validating the information that has been pre-populated in the “Type of activity” and “Activity” columns.
- Use the major project milestones or project schedule provided by the project management team and confirm your CM activities align with their scedule.
- Then, fill in the dates and status.
- Once your dates are filled in, you can sort them by clicking the arrow in the column title and all your activities will be in sequential order.
- You can filter the information in any column (A to K) by clicking the arrow in the column title cell.

## PM-CM Integrated Plan
PM-CM Integrated Plan
Client name‒Project name Address
Created by: xxxx | [9 empty] | Legend: | Not started |  |  |  |  | On track |  |  |  |  | Delayed |  |  |  |  | Late |  |  |  |  | Complete
[5 empty] | Project start date: |  |  | 2022-08-01
[5 empty] | Scrolling increment: |  |  | 0 |  |  | août | [34 empty] | septembre
Date : xx-xx-xx | time axis 2022-08-01 to 2022-09-25
Project phase | Type of activity | Activity | Lead | Notes | Status | Progress | Start date | End date | Actual end date | Days | bar: 2022-08-01 to 2022-09-25
Pre-planning and planning | Engagement | EXAMPLE ACTIVITY | John Doe |  | Delayed | 80% | 2022-08-01 | 2022-08-14 |  | 13
Pre-planning and planning | CM Program | CM Workbook |  |  | Not started |  |  |  |  | 1
Pre-planning and planning | CM Program | CM Strategy |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | Communication | Project announcement |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | Engagement | Employee townhall |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | Communication | Design survey invitation |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | Engagement | Removal of personal & business assets |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | Engagement | Change agent network |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | Communication | Communication channel(s) and content |  |  | Not started | 0% |  |  |  | 1
Implementation | Training | Manager toolkit |  |  | Not started | 0% |  |  |  | 1
Implementation | Communication | Floor plan announcement |  |  | Not started | 0% |  |  |  | 1
Implementation | Engagement | Boardroom naming |  |  | Not started | 0% |  |  |  | 1
Implementation | Training | A day in the life presentation |  |  | Not started | 0% |  |  |  | 1
Implementation | Engagement | Community norms for the new workplace (etiquette) |  |  | Not started | 0% |  |  |  | 1
Implementation | Engagement | Team charters |  |  | Not started | 0% |  |  |  | 1
Implementation | Training | Training content |  |  | Not started | 0% |  |  |  | 1
Implementation | Communication | Pre-opening announcements |  |  | Not started | 0% |  |  |  | 1
Implementation | Training | Employee toolkit/user guide |  |  | Not started | 0% |  |  |  | 1
Implementation | Engagement | Pre-opening townhall |  |  | Not started | 0% |  |  |  | 1
Implementation | Engagement | Tour of the new workplace |  |  | Not started | 0% |  |  |  | 1
Implementation | Engagement | Hybrid opening ceremony |  |  | Not started | 0% |  |  |  | 1
Implementation | Communication | Communication (ongoing) |  |  | Not started | 0% |  |  |  | 1
Post occupancy | Communication | Change sustainment communiques |  |  | Not started | 0% |  |  |  | 1
Post occupancy | Communication | PSPC Project Story Collection |  |  | Not started | 0% |  |  |  | 1
Post occupancy | Communication | Workplace performance survey invitation |  |  | Not started | 0% |  |  |  | 1
Post occupancy | Training | Training refresher courses (ongoing) |  |  | Not started | 0% |  |  |  | 1
Post occupancy | CM Program | CM sustainment checklist |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Secret/classified network access |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Print-on-demand |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Audio-visual equipment (videoconferencing , Clickshare, etc.) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Collaboration tools and platforms (MS Teams, Miro, Slack, etc.) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Applications via phones (elevator, access card, booking system, etc.) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Booking system |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Cloud-based tools and software (Microsoft 365, OneDrive, etc.) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Wi-Fi: private and/or public |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Policies and directives adapted to hybrid working |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Community norms / team charters |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | OHS: Assignment of first aiders |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Interim work agreement / telework agreement |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Managing employees in a hybrid working model |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Onboarding of employees in a hybrid working environment |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Digitization (paper storage space reduction) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Imaging services |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Implementation of an information management system (GCdocs, SharePoint, EDRMS, OneDrive, etc) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Digitalization of processes |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Emergency procedures |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Access card system |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Working in a shared space |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Assignment of Fire Warden role |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Access to and working in an ecosystem of spaces |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Activity-based working environment: shared seating |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Activity-based working environment: workpoint variety |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Activity-based working environment: work zones |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Ergonomics, accessibility and inclusivity in all workpoints |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Smart office (lights, temperature regulation, auto blinds, etc.) |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Lockers |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | PM Program | Mini design survey (functional program) |  |  | Not started | 0% |  |  |  | 1
Pre-planning and planning | PM Program | Functional programming workshop |  |  | Not started | 0% |  |  |  | 1
Implementation | PM Program | Client approval on design |  |  | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
[5 empty] | Not started | 0% |  |  |  | 1
Purpose: This tool allows you to map out the change management (CM) activities against the major milestones of the project management (PM) plan, in one document. Throughout your project, it serves as a high-level plan to help you plan out the first steps of your change management program. More precisely, you can use this tool to align CM and PM activities in one document, as well as organize activities and deliverables in a sequential order, with or without dates. For information on how to use the automated features of this tool, please refer to tab PM-CM Integrated Plan How-to

## CM Activity Tracker
CM Activity Tracker
CM ACTIVITY | TYPE OF ACTIVITY | STRATEGY OBJECTIVE | INDICATORS | TARGET | EVALUATION METHOD | DATA COLLECTION |  | POSSIBLE CORRECTIVE ACTIONS
[6 empty] | Responsibility | Frequency
Communication activities (various - per your needs) | Communication | Inform | # of clicks on website # of visitors on website # of recurrent visitors on website # of participants in Teams Channel # of feedback received % of opened/read email communications |  | Reports | Communications team/Change manager | Every two weeks
Employee townhalls | Engagement | Involve | # of participants # of questions received in chat/Q&A platform # of feedback received | [EXAMPLE: 60% participation rate for employees, 90% for people managers and 100% for senior leaders] | Observation | Change manager | During and after every townhall
Boardroom naming | Engagement | Involve | # of participants # of names received |  | Observation | Change manager | During and after the activity
Community norms for the new workplace (etiquette) | Engagement | Involve | # of participants # of questions received |  | Observation | Change manager | Every month
Team charters | Engagement | Involve | # of participants |  | Observation | Managers | During the activity
Tour of the new workplace | Engagement | Involve | # of participants # of feedback received |  | Mini survey | Change manager | During and after the activity
Hybrid opening ceremony | Engagement | Involve | # of participants in person # of participants online # of participants to in person tours # of feedback received |  | Observation | Change manager | During and after the activity
Training activities (various - per your needs) | Training | Equip | # of participants # of feedback received |  | Mini survey | Change manager | During and after the activity
A day in the life presentation | Training | Equip | # of participants # of feedback received |  | Mini survey | Change manager | During and after the activity
Workplace performance survey invitation | Communication | Reinforce | # of respondants to the survey |  | Report | PSPC | After the closing of the survey
This planning tool allows you to establish which change management activities you will need to track during your project. The Strategy objectives are linked to your Change Management Strategy. Tactical effectiveness should be measured after each activity, to ensure the activity has met its objective and target. If the activity does not meet its target, use the Possible corrective actions column to make improvements. Use the feedback and data gathered to enhance future iterations of the activities.
Purpose: The information gathered with this tool can help demonstrate the effectiveness of your change management program, the return on investment (ROI) and the overall value of the program.

## Data list PRET (hidden)
Organizational vision
We have a clear vision | The vision is aligned with GoC vision
We somewhat have a clear vision | The vision is somewhat aligned with GoC vision
We don’t have a clear vision | The vision is not aligned with GoC Vision
Sponsorship
Our strategy is supported | The sponsor has necessary authority
Our strategy is somewhat supported | the sponsor somewhat has the necessary authority
Our strategy is not supported | the sponsor does not have the necessary authority
Leadership
workplace modernization is a priority to our leaders | Leaders are ready to communicate
workplace modernization is somewhat a priority to our leaders | leaders are somewhat ready to communicate
workplace modernization is not a priority to our leaders | leaders are not ready to communicate
Key enablers
We have a modernization strategy | We have the necessary resources
We somewhat have a modernization strategy | We somewhat have the necessary resources
We do not have a modernization strategy | We don’t have the necessary resources
change management, communications and training
We have a structured change management approach | We have the necessary resources
We somewhat have a structured change management approach | We somewhat have the necessary resources
We do not have a structured change management approach | We don’t have the necessary resources
history of change
Our history of change is very successful | Employees embraced the changes
Our history of change is somewhat successful | Employees did not always embrace the past changes, and sometimes reverted to old ways
Our history of change is not successful | Employees did not embrace past changes, and almost always reverted to old ways
Culture of Innovation
We are open | Employees are rewarded
We are somewhat open | Employees are somewhat rewarded
We are not open | Employees are not rewarded
Leadership and Managers
Senior leaders and managers are highly skilled | Performance is evaluated based on results and not based on employees' presence
Senior leaders and managers are somewhat skilled | Performance is evaluated inconsistently, sometimes based on results and sometimes based on employees' presence
Senior leaders and managers are not very skilled | Performance in not evaluated based on results and based on employee's presence
Hybrid Work
Employees are encouraged, trusted and empowered | Remote work is supported
Employees are sometimes encouraged, trusted and empowered | Remote work is somewhat supported
Employees are not encouraged, trusted and empowered | Remote work is not supported
STATUS
N/A
Completed
In progress
Not started
Low
Medium
High
Enthusiast
Neutral
Resister
Impacted (I)
Indirectly Impacted (II)
Sponsors (S)

## Data list CM-PM (hidden)
Phase
Pre-planning and planning
Implementation
Post occupancy
Category
CM Program
PM Program
Communication
Engagement
Training