## Slide 1: Program example for change agent network activities
A guide for change managers
Version 1
Date: November 2023

## Slide 2: About this program
This program is aimed at change managers who support workplace modernization or transformation programs. It complements the Establishing a Change Agent Network guide by proposing concrete ideas for activities to be carried out with the network throughout the project, and even afterwards. These ideas are designed to help network members fulfill their role.
This document contains the following activities:
  Launch the Change Agent Network and share project update
  Get feedback from the Network
  Ensuring that the Change Agents Network supports learning about new developments in the workplace
  Preparing the Change Agents to support the move to the new workplace
  Transition the Network to a Change Management Committee
*The French version of this document is available here : FR version

## Slide 3: Launch the Change Agent Network and share project update
Activity | Details / Suggested Agenda | Available tools | When
Launch Change Agent Network | Agenda for the first meeting Welcome from the Project Sponsor Presentation of the project team Change Agents introductions Introduction of the Change Agent’s role and Toolkit content Presentation of communication tools (FAQ, Intranet, Teams, email) Project update Question period | Change Agent Toolkit Suggestion: If you're launching the Network in person, start with an icebreaker so that Change Agents can get to know each other! | During Phase 1 - Planning
Touchpoint meetings (30 minutes or less) | Agenda Project update Question period |  | Occasionally, when there are fewer elements to share.
Employee readiness meetings | Ask Change Agents to complete the Change Management Monitoring Questionnaire before the meeting. Compile results Present the results to the agents and discuss the items with the lowest scores to find possible solutions and implement corrective measures. | Change Management Monitoring Questionnaire | At the end of Phase 1 Planning and Phase 2 Implementation. Punctually at a time you consider appropriate.

## Slide 4: Getting feedback
Activity | Details / Suggested Agenda | Available tools | When
Floor plan presentation | Agenda Project update Return on the floor plans Return on the zoning and work points Questions and feedback Recommendation: The Project Sponsor should participate in the presentation and answer questions. | The Change Management Program-in-a-Box includes a floor plan announcement and a layout diagram in section 2.2. | After the Floor plan announcement to all staff so that Change Agents can gather feedback from their colleagues.
"A day in a life" presentation | Agenda Project update "A day in a life" presentation Question and feedback period | The Change Management Program in a Box includes the "A day in a life" (2.6). | During Phase 2 - Implementation.
Community Norms and etiquette presentation | Agenda Project update Community Norms and Workplace etiquette presentation Questions and feedback period | You will find in the Change Management Program box: Community Norms posters (2.4); Workplace Etiquette Posters (2.8). | During Phase 2 - Implementation.
The presentations below will help Change Agents fulfill their roles of providing you with information and raising issues. You should do some of these activities before they are carried out with all staff.
This will allow you to improve and adjust the content according to elements specific to your organization, or elements that raise concerns, as well as anticipating questions that staff may ask you.

## Slide 5: Support the learning of new ways of doing things
The activities below will help your Change Agents Network to fulfill their role of supporting staff integration and learning. By training them beforehand in the new workplace, they will be able to support their colleagues themselves.
Activity | Details / Suggested Agenda | Notes | When
Guided tours | To become familiar with the GC Workplace concept, the Change Agent Network could: Visit the GC coworking demonstration center at PDP IV Be among the first groups to visit the site once modernization is complete | The Change Management Program-in-a-Box includes the Virtual Tour Presentation Template and the In-Person Tour Speaking Points(2.10). | During Phase 2 - Implementation.
Demonstrations | Demonstrate : How to use the workstation reservation platform and book meeting rooms How to adjust your workstation ergonomically How technological and audio-visual equipment works in meeting rooms | Ask the project team to conduct these demonstrations! These sessions should be held in person, so that agents can test the equipment. | The weeks preceding the opening of the workplace.

## Slide 6: Move-in support
Activity | Details / Suggested Agenda | When
Support for business and personal property removal activities | Change Agents can become an extension of the teams responsible for asset removal activities (usually led by Information Management and Accommodations) by: Providing on-site support to staff. | To be determined with the project team.
Welcome and guide | When opening the workplace, Change Agents can: Join the Welcoming Committee; Offer guided tours; Make rounds on the floors to answer questions. | During opening week (See Change Management Program in-a-Box, 2.11 Opening week).
Post-occupancy support | Make sure that Change Agents are well known within your organization, so that staff can refer to them when necessary. Communicate their names and contact details on the intranet; Indicate how they can help their colleagues: with audio-visual equipment, the reservation system, the ergonomics of their workstation, etc. | If your organization has adopted a hybrid work model, allow up to 6 weeks for staff to become comfortable with the new workplace.
Now that you've created a network of experts on the modernized workplace, you can use your Change Agents to support staff as they integrate the workplace.
For these activities, consider making the Change Agents visible with an accessory such as a badge or sweater.

## Slide 7: Transitioning the Network to a Change Sustainment Committee
Once you've settled into your new work environment, consider holding a final meeting with the Change Agent Network and turning it into a Change sustainment committee.
These activities will take place in Phase 3 of the project – Post occupancy.
Activity | Details / Suggested Agenda | When
Post-mortem | Organize a meeting to evaluate: What went well, what didn't? What questions did employees ask and what issues did they encounter? | 6 weeks after the official opening
Feedback meetings | Organize meetings to gather Change Agents' observations on various elements, and to discuss possible solutions to remedy certain issues. Here are a few examples of what you can discuss: Do staff use the reservation system correctly? Are community norms and etiquette respected? What's a challenge in the new workplace? Are there any elements that continue to generate resistance? | The frequency could be every 4 to 6 weeks.
Welcoming new employees | Members of this Committee could be involved in welcoming new employees. Their tasks could include: Offer a guided tour of the workplace, introducing work points and etiquette; Be available to support new employees in all aspects of the workplace (reservation system, audio-visual, etc.). | If required