## Program Checklist
| Project: | STI Guidelines
| Publication: | STI Guidelines - Herpes
| Target Publication date | 2020-10-31
| Publication Milestones | Estimated time | Planned Start date | Planned End date | Planned Start date | Actual End date | Comments
Planning | Propose publication to Director | 1 week
| Consult other Divisions on possible intersections with their work | 1 week
| Complete Knowledge Mobilisation (KM) Planning Template | 1 week
| Add deliverables and milestones to PMR | 1 day
| Director approves publication deliverables and milestones in PMR | 2 weeks
| Engage stakeholders and governance bodies; gain collaboration, concurrence and approvals as appropriate | 1 month
Checklist for Pre-Development of Report | Develop CSR (Part 1) As soon as PMR aproved | 1 week
| MGR approval of Communications Services Request Form (Part 1) | 1 week
| Send CSR (Part 1) for StratComms Approval | 1 hour
| StratComms Review and Approval of CSR (Part 1) | 2 weeks
| DIRECTOR approval of CSR (Part 1) | 1 week
| Approved CSR (Part 1) to StratComms, hc.webcommunications.sc@canada.ca, hc.creative.services-creatifs.sc@canada.ca | 1 hour
| CSR (Part 2) sent by Comms with estimated timelines for proposed products (2-week service standard) *NOTE: Include estimates of number of tables/figures, as well as # of pages of text/ total # of pages. Include all possible products, even if internal resources may be used. Better to request and drop than not include. | 2 weeks | [5 empty] | *Estimates based on Calendar time, including Program QA time. Timelines should be considered additive, not concurrent.
| Negotiate timelines for Web, Graphic Design with Comms | 2 weeks
| Comms Approval | 3 day
| Update this document with estimated timelines from CSR (Part 2) | 1 hour | [5 empty] | MLISA comments: If the publication is not a routine surveillance report (ie not part of the agreed surveillance plan), but is using surveillance data, contact PTs whose data is to be used to get their concurrence and solicit their participation, if they so desire
| DG Approval of CSR (Part 2)- digital signature | 2 weeks
| Approved; back to program to be sent to CS/Comms | 1 hour
Writing | Planning of document structure (tables, graphics, format, audience) | TBD
| Consultations/Data acquisition/Analysis (Where the information is coming from) | TBD
| Development of document - English only | TBD
| QA of all tables | TBD
| Editing of document ($$) | TBD
| QA of Original draft | TBD
| Update Knowledge Mobilisation (KM) Planning Template with key messages | 1 day
| Review Knowledge Mobilisation (KM) Planning Template and action | 1 day
| Initiate development of linked KTE, if applicable | TBD
| Manager approval of Final Draft | 2 weeks | [5 empty] | *Includes time to discuss and edit
| Manager approval of Final KM template | 2 weeks | [5 empty] | *Includes time to discuss and edit
| Book Oral Briefing with DG (for shortly after deadline) to prevent delays once Reviewed Draft is ready (3-4 week lead time) | 1 hour
| Director approval of Final Draft | 2 weeks | [5 empty] | *Includes time to discuss and edit
| Create Long Descriptions of all figures/charts | TBD
Infographic (Pre-layout) | Identify content of interest/(Possibly) Sketch or mock up of proposed infographic | 2 weeks
| Develop an Infographic Plan (Word document) | 2 days
| Manager approval of Infographic Plan (Word document) | 1 week
| (If standalone infographic) Book Oral Briefing with DG 3-4 weeks before deadline for all feedback to be added | 1 hour
| Director approval of Infographic Plan | 2 weeks | [5 empty] | *Includes time to discuss and edit
| (If outsourcing) Get quote from contractor ALWAYS REQUEST SOURCE FILES! | 1 week
| (if outsourcing <5 k) Get CCM approval only - Credit card purchase - no call up needed | 1 day
| (if outsourcing >5 k) Call up/Standing offer/SFC/LFC | 2 weeks | [5 empty] | *dependent on workload/dollar value
Checklist for translation | Send documents/long descriptions for translation (in tandem with stakeholder feedback if FR not required) ($$) | 5 days | [5 empty] | *usually only 2-3, but 5 is conservative, especially for longer documents/busy periods.
| Translation | TBD
| QA translation (in-house or sourced out) | TBD
Stakeholder Feedback | Telecons with stakeholders if required | TBD | [5 empty] | MLISA requirements: for PT level aggregation 30 day review period required, for sub-PT analysis, written approval. When comments incorporated and final version is ready, can be sent to partners as an FYI with an embargo date, if desired.
| Send documents in English and French to stakeholders | 1 hour
| Prepare Notification Email for feedback or information | 1 week | [5 empty] | *Includes time for review and approvals if required
| Translation of Notification Email | 2 days
| Send Email Memo to stakeholders | 1 hour
| Make any applicable edits to the document in both translations | TBD
| Resend for translation of specific pieces if required | TBD
| Along the way, address all concerns | TBD
FYI to DG | DG briefing on Reviewed Draft/Infographic Plan (Book Oral Briefing 3-4 weeks ahead) | 1 hour
Checklist for translation and layout | Confirm final document(s) in both English and French (address any edits and translation needs) | TBD
| Send Creative Services/Contractor reviewed drafts in EN/FR to do design and layout | 1 hour
| CS/Contractor to do design/layout (Timelines as per CSR-2) | TBD
| Create Long Descriptions of any new figures/infographics | TBD
| Request ISBN/ISSN Number (form to CS) (if appropriate) | 1 hour
| Request Catalogue Number (CS) (if appropriate) | 1 hour
| Side by Side QA of French document (tables as well) | TBD
| Side by Side QA of English document (tables as well) | TBD
Web HTML (full report, exec summary, short reports, etc.) | Send Eng and French documents (and tables, figures, infographics) in Word and PDF to Web Publishing (email above) | 1 hour
| Make sure all linked documents are identified (especially if linked to another publication process such as CCDR) | 1 day
| Provide all necessary clarification re: URL, new or replacing, and anticipated date of release | 1 week
| If HIV/HEP, send embargoed PDF to CATIE to start coding (include final PDFs and short text paragraph to describe report) dmclay@catie.ca | 1 hour
| Provide all necessary clarification re: URL, new or replacing, and anticipated date of release to CATIE | 1 week
| QA all HTML English (including web links) | TBD
| QA all HTML French (including web links) | TBD
| Director informs DG of release, to add to her VP-DG Bilat ( FYI only) | 2 weeks | [5 empty] | *Depending on schedules for Director/DG and DG/VP bilats
Dissimination | Notification to E-Comms to go Live | 1 hour
| If Applicable, send live Canada.ca URLS to CATIE; inform them they can go live | 1 hour
| Prepare Notification Email(s) to all stakeholders | 2 days
| Translation of Notification Email | 2 days
| E-mail stakeholders | 2 days