## HLD overview
Dates (2wk) | Timing | Topic | Sub-topic | Day | Meeting Room | Activities | Participants
2018-08-20 | Week 1 | Current State (Upstream) | Source to Contract (Acquisitions Program - Goods) | Mon, Aug 20 (AM/PM) | Hunter | Understand the Source to Contract process today; people, process, tech, issues
|  |  | Contract- Complexity (Acquisitions Program - Goods) | Tue, Aug 21 (AM) | Hunter | Understand complexities in Contracting - contract clauses, contract simplification, complexity and risk assessment process (risk based approvals), complex contracting for major procurements
|  |  | E-tendering (Acquisitions Program - Goods) | Tue, Aug 21 (PM) | Hunter | Understand the e-tendering process; people, process, tech, issues
|  |  | Supplier Enablement (Acquisitions Program) | Wed, Aug 22 (AM) | Hunter | (AM) - Supplier onboarding, channels, process, policies
|  |  | Source to Contract (OGDs - Goods) | Thu, Aug 23 | Hunter | Discuss variations across departments
|  |  | No meetings | Fri, Aug 24 | X | Documentation/Prep
2018-08-27 | Week 2 | Current State (Downstream) | Procure-to-Pay (Acquisitions Program - Goods, OGDs Finance) | Mon, Aug 27 (AM/PM) | Bryson/Hunter | Understand the P2P (including catalogues) process today: people, process, tech, issues
|  |  | Services Procurement (Acquisitions Program) | Tue, Aug 28 (AM/PM) | Bryson/Hunter | (AM) - IT Services example; (PM) Construction Services example Understand the Services Proc process today: people, process, tech, issues
|  |  | Master data - vendor/item (Acquisitions Program + OGDs Finance) | Wed, Aug 29 (AM) | Rideau-Laughlin | Understand the vendor & item master mgmt process today: people, process, tech, issues
|  |  | Procure-to-Pay (OGDs - Goods + Services) | Thu, Aug 30 (AM/PM) | Bryson/Hunter | Discuss variations across departments | OGDs
|  |  | No meetings | Fri, Aug 31 |  | Documentation/Prep
2018-09-04 | Week 3 | Fit-gap against Ariba/ Fieldglass & Validation of Requirements | Holiday | Mon, Sept 3 - Labour Day |  | Internal working session to finalize draft fit-gap findings
|  |  | Requirements validation (Internal only, no meetings planned) | Tue, Sept 4 |  | Internal working session to finalize draft req'ts validation
|  |  | Ariba/ Fieldglass demos (Acquisitions Program + OGDs) | Wed, Sept 5 (AM) | Bryson for demo | SAP Ariba/FG demo to PSPC EPS team | All participants OGDs and PSPC of last 2 weeks. Advising participants in the email that there is limited space and provide webex information. Regions and other OGDs will be invited via webex. All questions will be asked/answered via the webex chat and minutes wil be provided afterwards.
|  |  | Supplier Enablement (External) | Wed, Sept 5 (PM) | Hunter for supplier enablement | Supplier community input | Emilio, Melissa, Stephanie Park, Olivier Goodman, 2 reps from OSME (already selected), 2 from treasury Board (already selected) **number of suppliers to be confirmed tomorrow Aug 30***
|  |  | Fitgap validation | Thu, Sept 6 (AM/PM) | Rideau-Laughlin/Ottawa | Playback fit-gap and requirements validation to PSPC | OGDs of last 2 weeks who supported discussions (list in second tab) + PSPC team
|  |  | No meetings | Fri, Sept 7 | X | Internal prep for following week Future State
2018-09-10 | Week 4 | Future State Design - Overall Vision | Procurement Modernization | Mon, Sept 10 (PM) | Hunter | Envisioning Procurement Modernization - what does this mean | PSPC champions + Management representatives of the departments that have been represented in previous weeks) (Emilio preparing a list as per Melissa's request) | Patricipants TBD
|  |  | Business Blueprint | Tue, Sept 11 (AM) | Hunter | Envisioning the E2E business (Procurement) blueprint | PSPC champions + Management representatives of the departments that have been represented in previous weeks) (Emilio preparing a list as per Melissa's request) | Patricipants TBD
|  |  | Procurement Roadmap | Tue, Sept 11 (PM) | Hunter | Envisioning the initial roadmap | PSPC champions + Management representatives of the departments that have been represented in previous weeks) (Emilio preparing a list as per Melissa's request) | Patricipants TBD
|  |  | Upstream | Wed, Sept 12 (AM/PM) | Ottawa/Colonel By | Upstream - E2E business process framework workshop (L1 - L3) | All participants OGDs and PSPC of last 2 weeks
|  |  | Downstream | Thu, Sept 13 (AM/PM) | AM: Ottawa PM: Hunter | Downstream - E2E business process framework workshop (L1 - L3) | All participants OGDs and PSPC of last 2 weeks
|  |  | No meetings | Fri, Sept 14 | X | Internal documentation
2018-09-17 | Week 5 | Future State Design - Business Processes | Business Process Design (Internal, no meetings) | Mon, Sept 17 | X | Internal team/documentation
|  |  | Business Process Design (Internal, no meetings) | Tue, Sept 18 | X | Internal team/documentation
|  |  | Business Process Design (Acquisitions Program + OGD) | Wed, Sept 19 | Rideau-Laughlin | Business process validation workshop (upstream) | PSPC and OGD champions (see next tab)
|  |  | Business Process Design (Acquisitions Program + OGD) | Thu, Sept 20 | Rideau-Laughlin | Business process validation workshop (downstream) | PSPC and OGD champions (see next tab)
|  |  | No meetings | Fri, Sept 21 | X | Internal documentation
2018-09-24 | Week 6 | Collaboration Hub | No meetings | Mon, Sept 24 | TBD | Internal prep
|  |  | Breakout team A: Sourcing Breakout Team B: Procure to Order | Tue, Sept 25 | TBD | Collaboration Hub | Champions from PSPC + OGD (see other tab) + regional representatives + a few selected suppliers (total number including EY + Infosys must be under or equal to 80) | Participant numbers to confirm with facilitator
|  |  | Breakout team A: Sourcing Breakout Team B: Procure to Order | Wed, Sept 26 | TBD | Collaboration Hub
|  |  | Breakout team A: Contracting Breakout Team B: Procure to order master data | Thu, Sept 27 | TBD | Collaboration Hub
|  |  | Breakout team A: Tendering Breakout Team B: Master data | Fri, Sept 28 | TBD | Collaboration Hub
2018-10-01 | Week 7 | Collaboration Hub | TBD | Mon, Oct 1 | TBD | Internal prep/documentation
|  |  | Breakout team A: Supplier enablement Breakout Team B: Services | Tue, Oct 2 | TBD | Collaboration Hub | Champions from PSPC + OGD (see other tab) (total number including EY + Infosys must be under or equal to 80) | Participant numbers to confirm with facilitator
|  |  | Breakout team A: Supplier enablement Breakout Team B: Services | Wed, Oct 3 | TBD | Collaboration Hub
|  |  | All participants: future state vision / end to end process walkthrough | Thu, Oct 4 | TBD | Collaboration Hub - Close/Sign-off/Celebration
|  |  | TBD | Fri, Oct 5 | TBD | Internal documentation
2018-10-08 | Week 8 | High Level Design | Final Deliverable | Mon, Oct 8 - Thanksgiving | X | Final documentation
|  |  | Final Deliverable | Tue, Oct 9 | X | Final documentation
|  |  | Final Deliverable | Wed, Oct 10 | X | Final documentation
|  |  | Final Deliverable | Thu, Oct 11 | X | Final documentation
|  |  | Final Deliverable | Fri, Oct 12 | X | Final documentation

## Champions
List of OGD champions per session
First Name | Last name | Department
Dan | Gee | Treasury Board Secretary – Acquired Services and Assets Sector
Thomas | Yiu | Treasury Board Secretary – Acquired Services and Assets Sector
Hana | Benabdallah | Land and Aerospace Equipment Procurement and Support Sector
John | Eng | Treasury Board Secretariat – Financial Management Transformation Sector
Dan | Simard | CNSC
Elizabeth | Wheeler | RCMP
Maha | Ghadieh | SSC
Parker | Kennedy | AAFC
Brian | Steele | CFIA
Mathieu | Lesage | DND
Harold | Lessard | CRA
Serge | Tshimanga | NRCan
Ashley | Williams | CBSA
Josephine | Dahan | CBSA
List of PSPC champions
First Name | Last name | Department
Mejuine | Chow | PSPC - Services and Technology Acquisition Management Sector
Paul | Dorion | PSPC – Commercial and Alternative Acquisitions Management Sector
Assia | Yahi | PSPC - Strategic Planning, Administration and Renewal Sector
Domenic | Idone | PSPC - Acquisitions Program Transformation Sector
Stephanie | Park | PSPC - Acquisitions Program Transformation Sector
Nicole | Ross | PSPC - Acquisitions Program Transformation Sector
Emilio | Franco | PSPC - Acquisitions Program Transformation Sector
Melissa | Thompson | PSPC - Acquisitions Program Transformation Sector
Aline | Ngarukiyintwali | PSPC - Acquisitions Program Transformation Sector
Guy | Ranger | PSPC - Acquisitions Program Transformation Sector
Pascal | Bouchard-Phillips | PSPC – Commercial and Alternative Acquisitions Management Sector
Jo-Anne | Carriere | PSPC - Large Ship Construction Sector
Tanay | Patel | PSPC – Strategic Policy Sector
Kerry | Sisk | PSPC – Strategic Policy Sector
Olivier | Goodman | PSPC - Acquisitions Program Transformation Sector
Michel | Turbide | PSPC - Acquisitions Program Transformation Sector

## Ad Hoc meetings
Ad hoc Meetings Tuesday September 4
Priority | First Name | Last name | Email | Department | Objective | Questions to prepare | Location
1 | Harold | Lessard | harold.lessard@cra.arc.gc.ca | CRA | CRA has been using Ariba for 10 years, we want to know about the implementation and the challenges. | - What modules are you using? - Are you using Ariba for sourcing, contracting, purchasing, invoicing? -What were the biggest isssues through the implementation? -Are you leveraging the Ariba network? -What is working well for you in Ariba? -What were the biggest issues during the implementations? -What are your major gaps? -What are the biggest pain points? | EY office, 99 Banks, 12th floor, Ottawa room
2 | Aline | Ngarukiyintwali | aline.ngarukiyintwali@tpsgc-pwgsc.gc.ca | PSPC | Aline has been working with solutions architects, we would like to meet with the team. | -What is the future state vision of the system architecture -What are your timelines? -Do you intend to keep your ERP on premise? | EY office, 99 Banks, 12th floor, Ottawa room
3 | Maya | Schwartz | maya.schwartz@tbs-sct.gc.ca | Finance | Finance has been working with SAP and have entered the implementation phase. | -What changes have been implemented to the SAP requesitioning process? -Where does Ariba need to integerate into SAP based on these requirements? -Can you share current state documentation we can study during this meeting? | EY office, 99 Banks, 12th floor, Ottawa room
4 | Alain | Dorion | alain.dorion@tpsgc-pwgsc.gc.ca | TPSGC | This group performs complex contracts for construction, a participant last week suggested we meet with Alain since he will have a lot of deviations to signal. | -Identify the deviations and pain points in the process maps ? -How are your contracts structured differently from typical PSPC contracts? -Walk us through the typical lifecycle of a contruction contract from source to settle | EY office, 99 Banks, 12th floor, Ottawa room
5 |  |  |  | DND | We wish to meet with DND to understand the deviation and variations in their process. It was indicated to us that they vary from the existing process, especially from a sensitive standpoint. | -How is the source to contract and P2P process different for a sensitive purchase? -Walk us through your vendor master data creation and maintenance process? -Identify the deviations and pain points in the process maps in attachment? -How are your contracts structured differently from typical PSPC contracts? -How is the source to contract process different for a sensitive purchase? | EY office, 99 Banks, 12th floor, Ottawa room
6 | Richard | Moores |  | SSC | SSC has Ivalua, we want to understand how this fits with Ariba | - You only use the Ivalua buying module, conifrm how the sourcing purchasing receiving and invoicing is performed. - Are you using Ivalua for sourcing, contracting, purchasing, invoicing? -What were the biggest isssues through the implementation? -Are you leveraging the Ivalua network? -What is working well for you in Ivalua? -What were the biggest issues during the implementations? -What are your major gaps? -What are the biggest pain points? | EY office, 99 Banks, 12th floor, Ottawa room