## Instructions
Change Readiness Assessment
Purpose
Assessing the organization’s readiness is one of the steps involved in developing a high-level change management strategy. Each organization has unique characteristics that make change management easy or challenging. This tool enables you as the change manager to quickly scan and understand your organization's readiness to determine if the conditions for success are in place to implement change management. The results could identify challenges, gaps and opportunities to be addressed before rolling out a change management strategy. Some organizations are ready, willing and able to change while others are severely lacking change experience or have a bad history of change. Knowing which one you are dealing with is critical at the beginning of the journey.
Tactic/approach
This assessment is to be completed by the change management team. Some responses might have to be gathered in collaboration with other partners. These organizational elements are important to understand so that the project team, including the change management team and leadership team, can successfully prepare and implement a successful change management strategy. To complete the assessment, simply answer each question using a scale of 1 to 5. The results will be on the "Results and guidance" tab.
WHAT YOU ARE MEASURING
-Leadership's, organization's and employees’ predisposition to change and change readiness
-Organizational culture in terms of its adaptability to change
-Leadership styles
-Readiness for implementation of change management

## Questionnaire
ORGANIZATIONAL VISION and LEADERSHIP READINESS: the right vision for the right workplace |  | 0 1 to 5 (N/A) (no) (yes) | % / 100 | element assessed
1 | Our organization has a clearly defined vision for our workplace transformation which is aligned with our mission, mandate and business objectives |  |  | Vision
2 | Leaders in our organization have made workplace modernization a priority |  |  | Vision and Priority
3 | The workplace transformation strategy is being supported by a project sponsor (person who is an advocate for the project and is focused on the benefits for the organization) |  |  | Project Sponsor
4 | The project sponsor can be active and visible throughout the entire project |  |  | Leadership Competency
5 | The workplace transformation strategy is being supported by a sponser (a person who can authorize, fund and have authority over the delivery) |  |  | Champion
6 | The sponser has the necessary authority over the people, processes and systems to authorize and fund the necessary changes (i.e. key enablers) |  |  | Champion
7 | Leaders in our organization are ready to communicate this change in the context of other competing priorities |  |  | Leadership Competency
8 | Leadership in our organization is willing and able to walk the talk |  |  | Leadership Competency
9 | Leadership will visibly reinforce the change and celebrate successes with the team and the organization |  |  | Leadership Competency
10 | Our organization is committed to its alignment with the Government of Canada’s vision of a modern, flexible and agile public service |  |  | Vision
| The executive sponsor can build awareness of the need for the change (why the change is happening) directly with employees |  |  | leader competency
| Leadership is willing and able to manage resistance from other managers and supervisors |  |  | leader competency
| The project sponsor and the champion are able to build a sponsorship coalition for the change |  |  | sponsor
| Leaders in our organization have linked key performance indicators and financial objectives to the workplace transformation. |  |  | vision priority | Project Mgmt Readiness | 0 | 100
|  | 0 | 0
CULTURE AND CHANGE READINESS: the right openness to adopt new ways of working |  | 0 1 to 5 (N/A) (no) (yes) |  | element assessed
1 | Our organization’s history of changes is successful |  |  | Change Competency
2 | Our organization is open to new ideas and innovation |  |  | Innovation
3 | People in our organization are rewarded for risk taking and embracing change |  |  | Innovation and Culture
4 | This is the right time to implement workplace transformation (i.e. it will not compete with other major changes currently being made) |  |  | Readiness
5 | Senior leaders and managers in our organization are highly skilled at managing change |  |  | Change Competency
6 | Employees in our organization have embraced past changes and did not revert back to old ways |  |  | Change Competency
7 | Our organization has a culture of supporting flexible ways of working |  |  | Culture
8 | Performance is evaluated based on results and not based on employees’ presence at the office |  |  | Culture
9 | Employees in our organization are encouraged, trusted and empowered to make choices about when, where and how they work based on what makes sense |  |  | Culture
10 | Remote work (i.e. telework) is supported with policies, agreements and/or other mechanisms |  |  | Culture
2 | Employees in our organization perceive past changes as positive |  |  | change competency
14 | The culture of our organization emphasizes the importance of teamwork, information sharing and collaboration |  |  | culture
3 | Employees in our organization view change as an opportunity |  |  | change competency
|  | 0 | 0
IMPLEMENTATION READINESS: the right conditions for the project's success |  | 0 1 to 5 (N/A) (no) (yes) |  | element assessed
1 | The workplace transformation objectives are aligned with the organization's strategic priorities |  |  | Priority
2 | Our organization has developed a workplace transformation strategy |  |  | Strategy
3 | Resources for the implementation of the workplace modernization strategy are available |  |  | Resources
4 | The champion is setting up an integrated approach to the project’s implementation |  |  | Project Integration
5 | A maestro (project integrator) has been identified to integrate all the key enablers (from IM, IT, HR, Security and Facilities) of the modernization project |  |  | Project Integration
6 | Captains (subject matter experts) representing all key enabling sectors (IM, IT, HR, Security, Facilities) included in the integrated delivery approach have been identified |  |  | Project Integration
7 | Resources for change management have been identified and trained |  |  | Resources
8 | A structured change management approach is being applied to the project |  |  | Change Management
9 | Resources to provide training to employees are available |  |  | Resources
10 | Resources to provide communication advice and develop communications products are available |  |  | Resources
3 | Resources to implement key enabling elements in all functional areas included in the integrated delivery approach (IM, IT, HR, Security, Facilities) are available |  |  | resources
|  | 0 | 0
|  | 0 | 0

## Results and guidance
Results and guidance
LEADERSHIP AND ORGANIZATIONAL READINESS
Elements to expect when ready to modernize
Successful organizations have a well-defined purpose and a direction defining the organizational and strategic objectives which express the organization’s vision for the future workplace.
Members of the organization have the ability to influence the decisions that have an impact on the work they perform. Employees feel that the tasks performed lead to the fulfilment of the set objectives.
Innovation and openness to change are promoted and there is a clear vision and defined objectives of what they wish to achieve by transforming their organization.
Objectives, benefits for the change, performance measurement indicators and a vision to guide the workplace modernization are identified and well defined. Those established foundational elements will support a smoother implementation.
Leadership is participating actively and visibly throughout projects, building coalitions and communicating directly with employees about why the workplace change is needed (number one contributor to successful change). Leadership understands the reasons for the change, can articulate them and can be a visible early advocate of the modernized workplace. This drives the organization to reach its goals and respect its vision.
Tips for the change manager
Make sure to create opportunities for the leader to be active and visible.
Establishing the vision by clearly defining and communicating what is to be achieved is key to implementing a modernized workplace. Senior management must be engaged in this visioning to set the scope and approach of the transformation initiative, from there Identifying the right executive leader and senior managers responsible for key decisions, engaging counterparts and building coalitions, and communicating the vision.
Ensure the leadership has the right change management skills to lead the project. Coach and train them if necessary.
Ensure senior management is fully onboard with this project as moving to a modernized workplace will require strong support and advocacy from them.
CULTURE AND CHANGE READINESS
Elements to expect when ready to modernize
Your organization knows how to manage and support changes; employees demonstrate an ability to deal positively with changes as opposed to ignoring or resisting them. The organization has a long history of success at managing major transformational projects or implementing initiatives. The workforce is agile and delivers by results, and a relationship of trust has been established. A modernized workplace provides a design that builds on these attributes.
The organization has developed the right tools, mindsets and framework to support empowered employees for greater flexibility and mobility. Changes in the culture, policies and directives such as performance management by results or telework have been made; the relationship between managers and employees is based on trust and performance results are key.
Senior management and managers have developed change management competencies, have potentially been trained in change management and understand clearly their roles to ensure communication, support and feedback with employees .
Tips for the change manager
Develop managers' and supervisors' competencies to become effective coaches and change managers. Enable your managers and supervisors to introduce, manage and reinforce change with their employees.
Employees prefer managers and supervisors to send change messages as they are the people whom they trust. Make sure to support managers by providing toolkits specifically created for them.
Create customized communications based on the organization's culture. This includes the mode of communication, the sender of messages, and the structure and content of a message. The right language for the culture must be used.
Coaching and training in change management might be an element to include as part of your strategy if the change management competency is not maturely thought out by the management community.
IMPLEMENTATION READINESS
Elements to expect when ready to modernize
The appropriate resources are allocated to the workplace modernization project, including the project side and the change management side, as well as to manage the integration of the project. The key enabling resources are allocated (financial, facilities, human resources, IM, security, IT, OHS, etc.) for the project's success. The integration of all of those elements provides a solution that makes sense to the employees and makes the adoption rate higher.
Tips for the change manager
A team structure, sometimes called a governance structure, should be established and should include the executive leader, champion, sponsor, project leads, a change manager, and the various key enabler leads (financial, human resources, security, IT, communication, OHS, etc.) for the workplace transformation project.
Before establishing a governance and project structure, the sponsor who has the necessary influence over the people, and authority over processes, funds and system should be identified and set the governance that should be put in place.

## Sheet1 (hidden)
| Current score | Ready to implement change
Organizational Vision and Leadership Readiness | 0 | 100
Culture and Change Readiness | 0 | 100
Implementation Readiness | 0 | 100