## Planner
|  | Select planned GC EARB date: |  |  | 2023-03-02
Day-zero offset | Week | Day | Calcluated dates | DoW | Stat Holiday Conflict | Timeline instructions boilerplate | Timeline instuctions with dates
-28 | W-minus-4 | D-minus-28 | 2023-02-02 | Thursday |  | – First draft (English only) required to be submitted to TBS EA team at EA.AE@tbs-sct.gc.ca. | 1. Thu. Feb. 02 – First draft (English only) required to be submitted to TBS EA team at EA.AE@tbs-sct.gc.ca.
-22 | W-minus-4 | D-minus-22 | 2023-02-08 | Wednesday |  | – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback | 2. Week starting from Wed. Feb. 08 – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback
-14 | W-minus-2 | D-minus-14 | 2023-02-16 | Thursday |  | – Updated draft (English only) is due by noon. To be collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide. | 3. Thu. Feb. 16 – Updated draft (English only) is due by noon. To be collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide.
-7 | W-minus-1 | D-minus-7 | 2023-02-23 | Thursday |  | – Pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck. | 4. Thu. Feb. 23 – Pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck.
-6 | W-minus-1 | D-minus-6 | 2023-02-24 | Friday |  | – Final deck (both English and French) is due at noon for distribution to GC EARB members. (Presenting department is responsible for translation of the content added in the main template, including all diagrams. TBS EA will ensure translation of the EA assessment slide.) | 5. Fri. Feb. 24 – Final deck (both English and French) is due at noon for distribution to GC EARB members. (Presenting department is responsible for translation of the content added in the main template, including all diagrams. TBS EA will ensure translation of the EA assessment slide.)
0 | W-zero | D-zero | 2023-03-02 | Thursday |  | – GC EARB session | 6. Thu. Mar. 02 – GC EARB session
4 | W-plus-1 | D-plus-4 | 2023-03-06 | Monday |  | – Meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion | 7. Week of Mon. Mar. 06 – Meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion
Copy-pasta of Timeline instuctions with dates (for email send-out)
1. Thu. Feb. 02 – First draft (English only) required to be submitted to TBS EA team at EA.AE@tbs-sct.gc.ca. 2. Week starting from Wed. Feb. 08 – TBS EA will set up a meeting between your team, TBS EA, SSC EA and CCCS on that week to go through the deck and provide feedback 3. Thu. Feb. 16 – Updated draft (English only) is due by noon. To be collected in a package for co-chairs’ pre-brief. TBS EA analyst will complete EA assessment slide. 4. Thu. Feb. 23 – Pre-brief with the co-chairs of GC EARB. Any input from the co-chairs will be relayed back to you for further update to the deck. 5. Fri. Feb. 24 – Final deck (both English and French) is due at noon for distribution to GC EARB members. (Presenting department is responsible for translation of the content added in the main template, including all diagrams. TBS EA will ensure translation of the EA assessment slide.) 6. Thu. Mar. 02 – GC EARB session 7. Week of Mon. Mar. 06 – Meeting with Committee Secretariat to do live-edit of the draft GC EARB Record of Discussion
Formulas:
Calcluated dates = F1+[Day-zero offset]
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this date be moved up by 1 or 2 days?

## GC EARB dates
GC EARB dates | Conflict dates | Conflict message | Conflict DoW
2023-03-02 | 2023-04-07 | Good Friday | Friday
2023-03-16 | 2023-04-10 | Easter Monday | Monday
2023-03-30 | 2023-05-22 | Victoria Day | Monday
2023-04-13 | 2023-06-24 | Fete Nationale (SJB) | Saturday
2023-04-27 | 2023-07-01 | Canada Day | Saturday
2023-05-11 | 2023-08-07 | August civic holiday | Monday
2023-05-25 | 2023-09-04 | Labour Day | Monday
2023-06-08 | 2023-10-02 | Truth & Reconcilation Day | Monday
2023-06-22 | 2023-10-09 | Thanksgiving Day | Monday
2023-07-06 | 2023-11-13 | Remembrance Day | Monday
2023-07-20 | 2023-12-25 | Christmas Day | Monday
2023-08-03 | 2023-12-26 | Boxing Day | Tuesday
2023-08-17 | 2024-01-01 | New Year's Day | Monday
2023-08-31
2023-09-14
2023-09-28
2023-10-12
2023-10-26
2023-11-09
2023-11-23
2023-12-07
2023-12-21
2024-01-04
2024-01-18
2024-02-01
2024-02-15
2024-02-29
2024-03-14
2024-03-28